## First Review Projects
REF # | MAP REF | PROJ # | PROJECT NAME | PLAN | PLAN | STATUS | FUNDING SOURCE | All Prior Years | Expenses | Expenses | Expenses | Expenses | Expenses | Expenses | Expenses | Expenses | Expenses | TOTAL PRIOR YEARS EXPENSES | BUDGET | PRELIMIN | BUDGET | $ | $ | CARRYOVER | $ | $ | CURRENT BUDGET FY 14/15 | AS OF | AS OF |  | CURRENT BUDGET FY 15/16 | CURRENT BUDGET FY 16/17 | CURRENT BUDGET FY 17/18 | CURRENT BUDGET FY 18/19 | CURRENT BUDGET FY 19/20 | 5 YEAR BUDGET | 6-10 YEAR BUDGETS | TOTAL PROJECTED COST | START UP |  | RECURRING
FUNDING SOURCE CODES: A = AD VALOREM; D = DEBT FINANCE; E = ENTERPRISE FUND; G = GRANT; GT = GAS TAX; I = IMPACT FEES; LA = LIBRARY AD VALOREM; S = SPECIAL; T = TDC; M = MSBU/TU
COMP PLAN CODES: R = REQUIRED; NR = NOT REQUIRED; F = FURTHERS SPECIFIC OR GENERALIZED REQUIREMENT OF LEE PLAN; CATEGORY CODE 1 THROUGH 5
1 |  |  | NATURAL RESOURCES
2 | D6 | 208574 | Briarcliff/Fiddlesticks Water Quality Improvements | 4 |  | Construction complete | A-30100 | 0 |  | 0 | 0 | 239041 | 543854 | 62140 | 1183658 | 53984 | 19688 | 2102365 | 0 | 130312 | 130312 | [5 empty] | 130312 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2232677
3 | CW | 208588 | Caloosahatchee SII for TMDL Compliance | 2 |  | BMAP completed | A-30100 | 0 |  | 4380 | 25789 | 0 | 0 | 21920 | 16844 | 31257 | 132382 | 232572 | 0 | 1269096 | 1269096 | [5 empty] | 1269096 | 0 | 0 |  | 1000000 | 2000000 | 2000000 | 2000000 | 2000000 | 9000000 | 30000000 | 40501668
4 | CW | 208589 | Charlotte Harbor TMDL Compliance | 2 |  | Awaiting FDEP direction | A-30155 | 0 |  | 2190 | 12894 | 0 | 0 | 0 | 0 | 634 | 5456 | 21174 | 0 | 1493 | 1493 | [5 empty] | 1493 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1209916 | 1232583
5 | CW | 208596 | Culvert Replacement | 3 |  | Permitting Complete | A-30155 | 0 |  | 0 | 14080 | 174613 | 51558 | 86572 | 75778 | 194498 | 487007 | 1084106 | 0 | 259056 | 259056 | [5 empty] | 259056 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1343162
6 | D6 | 203072 | Eagle Ridge/Legends Interconnect | 4 |  | Proposed | A-30155 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | CW | 208591 | Everglades-West Coast SII for TMDL Compliance | 2 |  | BMAP completed | A-30100 | 0 |  | 4380 | 25789 | 0 | 0 | 21920 | 105277 | 70796 | 30266 | 258428 | 0 | 585140 | 585140 | [5 empty] | 585140 | 0 | 0 |  | 200000 | 200000 | 200000 | 200000 | 200000 | 1000000 | 18000000 | 19843568
8 | B8 | 208548 | Fichter Creek Restoration | 5 |  | Permitting complete | A-30100,55 | 0 |  | 38591 | 170556 | 176793 | 8740 | 2753 | 6290 | 0 | 0 | 403723 | 0 | 78088 | 78088 | [5 empty] | 78088 | 0 | 0 |  | 0 | 1400000 | 0 | 0 | 0 | 1400000 | 0 | 1881811
9 | F7 | 208549 | Halfway Creek Filter Marsh | 4 |  | FDOT JPA approved | A-30100 | 0 |  | 18546 | 88280 | 97245 | 7443 | 178815 | 1800 | 32317 | 32029 | 456475 | 0 | 1109089 | 1109089 | [5 empty] | 1109089 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1565564
10 |  | 208572 | Hendry Creek W Branch Water Quality Imp |  |  | Proposed | A-30100 | [9 empty] | 0 | 0 | 400000 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 2500000 | 0 | 0 | 0 | 2500000 | 0 | 2500000
11 | E6 | 208546 | Island Park Filter Marsh | 4 | 85.1.1, 85.1.2, 85.1.3, 41.3.11 | Monitoring & Maintenance | A-30100 | 0 | 3741 | 820634 | 553516 | 98318 | 55249 | 37911 | 21255 | 9734 | 7930 | 1608288 | 0 | 10054 | 10054 | [5 empty] | 10054 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1618342
12 | D6 | 208513 | Lakes Park Water Quality Project | 5 |  | Construction complete | A-30100.G |  |  |  | 0 | 104465 | 301080 | 587 | 2138694 | 286538 | 20265 | 2851629 | 0 | 966572 | 966572 | [5 empty] | 966572 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3818201
13 | A6 | 208567 | Nalle Grade Stormwater Park | 4 |  | Negotiating Consultant Contract | A-30155 | [5 empty] | 0 | 0 | 403 | 34 | 101748 | 102185 | 0 | 797816 | 797816 | [5 empty] | 797816 | 0 | 0 |  | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | 3900001
14 | A,B6 | 208563 | NFM Surface Water Improvements | 1 |  | Negotiating Consultant Contract | A-30155 | [6 empty] | 0 | 0 | 0 | 29650 | 29650 | 0 | 270350 | 270350 | [5 empty] | 270350 | 0 | 0 |  | 1000000 | 1000000 | 1000000 | 0 | 0 | 3000000 | 0 | 3300000
15 | B5 | 208569 | Palmona Park Water Quality Improvements | 1 |  | In design & permitting | A-30100 | [5 empty] | 0 | 0 | 58922 | 39676 | 25782 | 124380 | 0 | 1126412 | 1126412 | [5 empty] | 1126412 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250792
16 | A6,7 | 208556 | Poling Lane Drainage | 1 |  | Construction complete | A-30100 | 0 |  | 10269 | 16515 | 5576 | 0 | 13243 | 37841 | 49050 | 0 | 132494 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132494
17 | A7 | 208593 | Popash Creek Preserve | 5 |  | Complete | A-30100 | 0 |  | 24767 | 226274 | 120169 | 37306 | 1072541 | 52646 | 13795 | 5273 | 1552771 | 0 | 6829 | 6829 | [5 empty] | 6829 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1559600
18 | B6 | 208584 | Powell Creek Hydrological Restoration | 4 |  | Monitoring filter marsh | A-30100 | 9631 | 34959 | 22062 | 150553 | 495722 | 105964 | 55991 | 2363377 | 186374 | 22960 | 3447593 | 0 | 127040 | 127040 | [5 empty] | 127040 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3574633
19 | A5 | 208561 | Prairie Pine Restoration | 5 |  | In design and permitting | A-30100 | 0 |  | 0 | 0 | 0 | 37900 | 14330 | 39070 | 77053 | 37982 | 206335 | 0 | 302665 | 302665 | [5 empty] | 302665 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 509000
20 | A9 | 208538 | Spanish Creek Restoration | 3 | Obj. 41.2 | In design and permitting | A-30100 | 6968 | 1740 | 0 | 187703 | 16615 | 4268 | 0 | 0 | 41535 | 258899 | 517728 | 0 | 327888 | 327888 | [5 empty] | 327888 | 0 | 0 | 205232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 845616
21 | C7 | 208557 | Sunniland/Nine Mile Run Drainage Improve | 3 |  | Proposed | A-30155 | [8 empty] | 0 | 0 | 0 | 100000 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 350000 | 0 | 0 | 0 | 0 | 350000 | 0 | 350000
22 | D6 | 202965 | Ten Mile Canal Filter Marsh | 5 |  | Construction Complete | A-30100 | 1646985 | 181250 | 93080 | 66094 | 346742 | 40434 | 97972 | 321410 | 1260088 | 52305 | 4106360 | 0 | 144640 | 144640 | [5 empty] | 144640 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4251000
23 | A5 | 208509 | Yellow Fever Creek Chain Improvements | 5 |  | On hold pending Cape Coral | A-30100 | 0 |  | 13035 | 95601 | 286 | 0 | 0 | 0 | 0 | 0 | 108922 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 571000 | 0 | 0 | 0 | 0 | 571000 | 0 | 679922
24 |  |  | NATURAL RESOURCES CAPITAL TOTAL |  |  |  |  | 1663584 | 221690 | 1051934 | 1633644 | 1875585 | 1193796 | 1666695 | 6423265 | 2347363 | 1269622 | 19347178 | 500000 | 7512540 | 7512540 | 0 | 0 | 0 | 0 | 0 | 7512540 | 0 | 0 |  | 6121000 | 7100000 | 3200000 | 2200000 | 2200000 | 20821000 | 49209916 | 96890634
25 |  | 208573 | Natural Resources Master Project |  |  |  | A-30100 | [11 empty] | 1700000 |  | 1700000 | [5 empty] | 1700000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
26
27 |  |  | TRANSPORTATION DEPARTMENT
28
29 | E6,7 | 204030 | Alico Road Multi-Laning | R | 36.1.1;36.1.4;38.2.5 | Acquiring maintenance access ROW | A,GT,I | 13859321 | 1752714 | 1976862 | 364087 | 1069710 | 80898 | 63445 | 58793 | 18104 | 2150 | 19246084 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19246084 |  |  | 09/10 | 124503
30 | B7,8 | 205075 | Alico Rd 4L - Ben Hill/Airport Rd | 5 |  | Preliminary design underway | GT,i25,A | [5 empty] | 0 | 34703 | 663598 | 0 | 214281 | 912582 | 0 | 1672579 | 1672579 | [5 empty] | 1672579 | 0 | 0 |  | 0 | 0 | 11500000 | 540000 | 0 | 12040000 | 0 | 14625161 |  |  | 15/16 | 45656
31 |  | NEW | Alico Rd Connection |  |  | Preliminary design underway | I25 | [10 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2240868 | 2240868 | 64000000
32 | CW | 206002 | Bicycle/Pedestrian Facilities | 4 | 40.4.2 | Daniels pathway complete | GT,I21-25 | 12382165 | 1151927 | 3009199 | 1692691 | 2422346 | 382378 | 31250 | 135022 | 225361 | 191171 | 18607940 | 770000 | 640905 | 1410905 | [5 empty] | 1410905 | 0 | 0 |  | 394000 | 2437000 | 1312000 | 843000 | 1161000 | 6147000 | 3700000 | 29865845 |  |  | 15/16 | 74949
33 | F6 | 205724 | Big Carlos Pass Bridge Replacement | 1 |  | Proposed | E30720 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 3500000 | 1500000 | 5000000 | [5 empty] | 5000000 | 0 | 0 |  | 3500000 | 3500000 | 3500000 | 3500000 | 1000000 | 15000000 | 25300000 | 45300000
34 |  | NEW | Big Hickory Pass Bridge Replacement |  |  | Proposed | GT | [10 empty] | 0 |  |  | 0 | [5 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 10043000 | 10043000
35 | C8 | 205720 | Bonita Beach Road - Phase II | 5 |  | Construction complete | I-24,A,S | 0 | 0 | 783432 | 1245327 | 555067 | 107744 | 310312 | 2891968 | 1977882 | 0 | 7871732 | 0 | 366000 | 366000 | [5 empty] | 366000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8237732 |  |  | 11/12 | 16680
36 | G7 | 205723 | Bonita Beach Road - Phase III | 5 |  | Design underway | I-24,A,S |  |  | 0 | 462543 | 795030 | 234741 | 282487 | 209463 | 1080 | 0 | 1994332 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 23700000 | 25694332
37 | E6,7 | 206758 | Briarcliff/Ripp Signalization | 3 |  | FDOT bidding construction | GT | [5 empty] | 0 | 0 | 0 | 225000 | 0 | 225000 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000 |  |  | 12/13 | 1300
38 | B,C4 | 204088 | Burnt Store Road Four Laning-78 to Van Buren | 5 |  | In design & purchasing ROW | E30721, A, I-22, S | 387571 | 2175358 | 1177479 | 1583139 | 573961 | 1543038 | 592703 | 212946 | 500290 | 882743 | 9571084 | 13325000 | 1364311 | 14689311 | [5 empty] | 14689311 | 0 | 0 |  | 6580000 | 5042246 | 897754 | 8700000 | 630000 | 21850000 | 0 | 46110395 |  |  | 15/16 | 8400
39 |  | NEW | Cape Coral Bridge WB Span Replacement |  |  | Proposed | E30721, A, I-22, S | [9 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 1000000 | 4000000 | 5000000 | 82500000 | 87500000
40 | C5 | 205601 | Cape/Midpoint Plaza Reconstruction | NR |  | Construction complete | E |  |  | 0 | 0 | 738570 | 2123852 | 6329018 | 5427272 | 868827 | 0 | 15487539 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15487539 |  |  | 09/10 | 5730
41 | D,E1 | 205053 | Captiva Drive Shoulders | 1 |  | Complete - Monitoring | GT | 0 | 34690 | 9610 | 1179829 | 3227 | 1600 | 1500 | 900 | 400 | 500 | 1232256 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1232256
42 | C7 | 204054 | Colonial Blvd/Six Mile to SR82 | 5 | 36.1; 36.1.5 | Major construction complete | I-23,A,S | 185937 | 498706 | 8163331 | 248125 | 1228763 | 7634075 | 8450645 | 2326833 | 1245002 | 245051 | 30226468 | 0 | 563426 | 563426 | [5 empty] | 563426 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30789894 |  |  | 11/12 | 86496
43 |  | NEW | Colonial Blvd Alternatives Analysis |  |  | Proposed | I23 | [13 empty] | 0 | [5 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 350000 | 0 | 350000 | 0 | 350000
44 | B5 | 205082 | Corbett Rd Widening/Resurfacing | 3 |  | Proposed | GT | [8 empty] | 0 | 0 | 0 | 150000 | 0 | 150000 | [5 empty] | 150000 | 0 | 0 |  | 690000 | 0 | 0 | 0 | 0 | 690000 | 0 | 840000
45 | E10 | 205065 | Corkscrew Curve | 1 |  | Ongoing vegetation maintenance | GT | 0 |  | 0 | 882059 | 21174 | 23100 | 30420 | 17580 | 3225 | 1500 | 979058 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 979058
46 | D6 |  | Crystal Drive 2 Lane Divided | 5 |  | construction | I23 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 850000 | 850000 | 1700000 | 5750000 | 7450000
47 | D6 | 205077 | Crystal/Plantation Roundabout | 4 |  | CONSTRUCTION | A | [7 empty] | 0 | 0 | 16687 | 1125 | 0 | 560339 | 560339 | [5 empty] | 560339 | 0 | 0 |  | 25000 | 0 | 0 | 0 | 0 | 25000 | 0 | 586464
48 | D7 | 205072 | Daniels 6L / Treeline-Gateway | 5 |  | Complete | I-23,A,GT | 0 |  | 0 | 0 | 0 | 375140 | 1676577 | 1716692 | 62724 | 0 | 3831133 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3831133
49 | D6,7 | 205079 | Daniels Resurfacing Six Mile to I-75 | 3 |  | Construction substantially complete | GT | [6 empty] | 0 | 0 | 1123880 | 8721 | 1132601 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1132601
50 | B,C,D5 | 205062 | Del Prado ROW | 5 |  | Waiting on final invoice from Cape | I | 0 |  | 196 | 0 | 1461848 | 938004 | 666727 | 33049 | 55 | 0 | 3099879 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3099879
51 | D5 | 206688 | Del Prado Signals/Resurfacing | 3 |  | Constuction underway | GT,S | [5 empty] | 0 | 24967 | 99333 | 776043 | 2502 | 902845 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 902845 |  |  | 12/13 | 2500
52 | C6 | 205038 | E-ARCS Upgrade for Leeway | 3 |  | Complete | E | 0 | 154114 | 0 | 0 | 190921 | 400722 | 72313 | 24829 | 13526 | 0 | 856425 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 856425
53 | E5 | 205067 | Estero Blvd Improvements | 3 |  | Preliminary design underway | GT,I-24,A |  |  | 0 | 573729 | 564674 | 305276 | 59303 | 97072 | 495621 | 516584 | 2612259 | 750000 | 8419621 | 9169621 | [5 empty] | 9169621 | 0 | 0 |  | 7000000 | 750000 | 7300000 | 750000 | 7000000 | 22800000 | 15500000 | 50081880 |  |  | 15/16 | 39600
54 | E7 | 205021 | Estero Parkway Extension | 5 |  | Landscaping phase | S,GT,A,I | 9234990 | 5150090 | 1166586 | 14520635 | 21315862 | 3160600 | 99029 | 2335966 | 32806 | 19475 | 57036039 | 0 | 11000 | 11000 | [5 empty] | 11000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57047039 |  |  | 09/10 | 125686
55 | D5 | 205605 | Fiber Ring | NR |  | Proposed | E | [7 empty] | 0 | 0 | 252909 | 252909 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252909
56 | D5 | 204083 | Gladiolus Widening | 5 | 21.1; 21.1.5 | A&W Bulb construction underway | A,GT,I-4,24 | 1606610 | 1678807 | 312416 | 2393046 | 7993290 | 6342722 | 311392 | 658966 | 2255502 | 106652 | 23659403 | 0 | 439108 | 439108 | [5 empty] | 439108 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24098511 |  |  | 10/11 | 107992
57 |  | NEW | Gunnery Rd/8th St Intersection Imp |  |  | construction | GT | [11 empty] | 0 | 0 | 0 | [5 empty] | 0 |  |  |  | 60000 | 850000 | 0 | 0 | 0 | 910000 | 0 | 910000
58 |  | 206689 | Hickory Blvd Paved Shoulders | 1 |  | Complete | GT | [5 empty] | 0 | 431420 | 58664 | 0 | 0 | 490084 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 490084
59 | C8 | 205063 | Homestead 4L / Sunrise-Alabama | 5 |  | Design & ROW acquisition underway | I-23,A,GT | 0 |  | 621983 | 1138204 | 342534 | 113098 | 28928 | 20294 | 65983 | 47583 | 2362189 | 1750000 | 2730668 | 4480668 | [5 empty] | 4480668 | 0 | 0 |  | 11605000 | 690000 | 0 | 0 | 0 | 12295000 | 0 | 19137857 |  |  | 16/17 | 95020
60 | C8 | 205080 | Homestead Road Complete Street | 3 |  | Design to begin in 4th quarter | GT | [7 empty] | 0 | 0 | 0 | 0 | 0 | 1500000 | 1500000 | [5 empty] | 1500000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
61 | B5 |  | Kismet/Littleton Realignment | 5 |  | Proposed | I-22 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 137500 | 675000 | 825000 | 0 | 1637500 | 0 | 1637500
58 |  | NEW | Lee Blvd/Gunnery Rd Intersectoin Imp |  |  | Proposed | GT | [13 empty] | 0 | [5 empty] | 0 | 0 | 0 |  | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | 500000
59 |  | NEW | Little Carlos Pass Bridge Replacement |  |  | Proposed | GT | [13 empty] | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3270000 | 3270000
60 |  | NEW | Little Pine Island Pass Bridge Replacment |  |  | Proposed | GT | [13 empty] | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3385000 | 3385000
60 | B7 | 205068 | Luckett Road 4L / Ortiz to I-75 | 5 |  | Finalizing ROW acquisition | I-23,A | 0 |  | 0 | 538832 | 151 | 0 | 0 | 11810 | 0 | 0 | 550793 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3519000 | 4069793
61 | C3 | 205904 | Matlacha Pass Bridge Replacement | 3 |  | Under construction | I-22, GT,A | 0 | 556136 | 2017433 | 377218 | 403776 | 819226 | 9443938 | 8807406 | 1658521 | 99380 | 24183034 | 0 | 1019534 | 1019534 | [5 empty] | 1019534 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25202568 |  |  | 11/12 | 1600
62 | CW | 205074 | Mitigation Bank |  |  | Ongoing permit discussions w/Corp | GT |  |  |  |  | 0 | 41773 | 41544 | 28826 | 14899 | 5457 | 132499 | 0 | 3502 | 3502 | [5 empty] | 3502 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136001
63 |  | NEW | New Pass Bridge Replacement |  |  | Proposed | E, GT | [20 empty] | 0 | 0 |  | 0 | 0 | 2700000 | 5000000 | 5000000 | 12700000 | 7060000 | 19760000
64 | C6 | 204100 | North Airport Road Extension West | 4 |  | In design by Developer | A, I-23 |  |  | 0 | 0 | 0 | 1350 | 235718 | 100358 | 92114 | 18284 | 447824 | 4195000 | 277177 | 4472177 | [5 empty] | 4472177 | 0 | 0 |  | 70000 | 0 | 0 | 0 | 0 | 70000 | 0 | 4990001 |  |  | 15/16 | 14524
65 | C6 | 205078 | North Airport Road Reconstruction | 3 |  | Design to begin in 4th quarter | GT | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66 | C7 |  | Ortiz 4L / Colonial-MLK | 5 |  | Proposed | I-23,A | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 1550000 | 0 | 0 | 1550000 | 13269000 | 14819000
67 | C7 | 205056 | Ortiz Avenue/SR80 - Luckett | 5 |  | ROW acquisition underway | I-23,A | 0 | 368814 | 2660268 | 2282520 | 1829137 | 643708 | 620568 | 1269 | 7432 | 920 | 8414636 | 0 | 3143703 | 3143703 | [5 empty] | 3143703 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 12450000 | 24008339
68 | C7 | 204072 | Ortiz Four Laning - MLK to Luckett | 5 | 37.1 POL 36.1.5 | ROW acquisition underway | I-23,A,GT | 78974 | 1301297 | 3377302 | 2110669 | 1516558 | 240660 | 115320 | 352093 | 65158 | 42840 | 9200871 | 0 | 604811 | 604811 | [5 empty] | 604811 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 9325000 | 19130682
69 |  | NEW | Palomino Lane Improvements |  |  | Proposed | S | [9 empty] | 0 | 0 | 0 | 132614 | 132614 | [5 empty] | 169636 | 0 | 0 |  | 80364 | 1700000 | 0 | 0 | 0 | 1780364 | 0 | 1950000
70 | C,D6 | 204065 | Plantation Ext., Idlewild to Colonial | 5 | 36.1;36.1.5 | In landscaping maintenance phase | I-4,A | 867849 | 238695 | 219112 | 3509648 | 2839952 | 504664 | 6674 | 135137 | 27394 | 11688 | 8360813 | 0 | 8092 | 8092 | [5 empty] | 8092 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8368905 |  |  | 09/10 | 54537
71 | CW | 206690 | Signal System Central Software | 3 |  | Complete | GT | [5 empty] | 0 | 305662 | 26365 |  | 0 | 332027 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 332027
72 | CW | 206759 | Signal System ATMS Upgrades | 3 |  | Installing fiber connections on Gladious, Corckscrew & Alico | GT | [5 empty] | 0 | 0 | 623277 | 800312.82 | 644528 | 2068117.82 | 750000 | 205925 | 955925 | [5 empty] | 955925 | 0 | 0 |  | 750000 | 750000 | 750000 | 750000 | 750000 | 3750000 | 0 | 6774042.82 |  |  | 15/16 | 9500
73 | D6 | 204604 | Six Mile Cypress Pkwy 4 Laning | 4 |  | Substantially complete | I-23,A | 122187 | 588732 | 307501 | 38265 | 109611 | 160166 | 2975441 | 3295397 | 462562 | 589359 | 8649221 | 0 | 309049 | 309049 | [5 empty] | 309049 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8958270 |  |  | 12/13 | 44806
74 | E5 | 206691 | Summerlin Bike-Ped Accommodation | 1 |  | Construction underway | GT | [5 empty] | 0 | 10213 | 13574 | 732263 | 0 | 756050 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 756050
75 | D6 | 206007 | Summerlin Road-Boy Scout to Cypress Lake | 5 | 36.1;36.1.5 | Finalizing drainage issues | GT,I-23,A | 2276006 | 419069 | 1332740 | 7894713 | 8577395 | 6490432 | 6419663 | 1444719 | 585831 | 451829 | 35892397 | 0 | 750000 | 750000 | [5 empty] | 750000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36642397 |  |  | 12/13 | 230731
76 |  | NEW | Sunshine Blvd/8th St SW Roundabout |  |  | Proposed | GT | [11 empty] | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 200000 | 200000 | 550000 | 950000 | 0 | 950000
77 | D7 | 204053 | Three Oaks Pkwy Extension, North | R | 36.1.1;36.1.4 | Design and ROW underway | I-24,A,GT | 1990373 | 79909 | 208499 | 3482379 | 608014 | 50814 | 361087 | 149075 | 6488 | 0 | 6936638 | 0 | 5690477 | 5690477 | [5 empty] | 5690477 | 0 | 0 |  | 0 | 0 | 3000000 | 0 | 3000000 | 6000000 | 37250000 | 55877115
78 | F7 | 204043 | Three Oaks Pkwy Extension, South | R | 36.1;36.1.5 | To construct pond | I,A,GT,S | 13608167 | 21534040 | 12771667 | 5899147 | 2254446 | 123559 | 32714 | 1083763 | 4218330 | 504068 | 62029901 | 0 | 303400 | 303400 | [5 empty] | 303400 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62333301
79 | E7 | 204081 | Three Oaks Pkwy Widening | 5 | 36.1;36.1.5 | Landscaping maintenance phase | I-24,A,GT | 9068861 | 400034 | 8389561 | 10342969 | 3022319 | 262357 | 272966 | 612907 | 52196 | 40871 | 32465041 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32465041 |  |  | 09/10 | 280098
80 | C5,E4 | 205818 | Toll Interoperability | 3 |  | Plans to modify lane equipment | E | [7 empty] | 0 | 0 | 0 | 0 | 0 | 150000 | 150000 | [5 empty] | 150000 | 0 | 0 |  | 150000 | 150000 | 150000 | 150000 | 150000 | 750000 | 0 | 900000
81 | C5,E4 |  | Toll System Replacement | NR |  | Proposed | E |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 2250000 | 2250000 | 0 | 0 | 4500000 | 0 | 4500000
82 | B7 | 205037 | Traffic Mgmt Center Update | 3 |  | Complete | GT,S | 0 | 11804 | 68630 | 16345 | 38419 | 25831 | 542 | 0 | 14057 | 8870 | 184498 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 184498
83 |  |  | TRANSPORTATION CAPITAL TOTAL |  |  |  |  | 65669011 | 38094936 | 48573807 | 62776119 | 60476755 | 33131528 | 40339189 | 33675216 | 18628868.82 | 4926603 | 403195326.82 | 25190000 | 32366241 | 57556241 | 0 | 0 | 0 | 0 | 0 | 57593263 | 0 | 0 |  | 31404364 | 18256746 | 35784754 | 23458000 | 26331868 | 135235732 | 320021000 | 849804453.82
84
85 |  |  | UTILITIES
86 | D9,E9 |  | Airport Mitigation Park ASR System | 5 |  | cancelled 15/16 | E | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | E7 | 207614 | Alico Rd 4L-Ben Hill/Airport Haul-WM Reloc | 3 |  | Per LCDOT schedule | E | [7 empty] | 0 | 0 | 3497 | 3497 | 0 | 196320 | 196320 | [5 empty] | 196320 | 0 | 0 |  | 0 | 0 | 3750000 | 0 | 0 | 3750000 | 0 | 3949817
88 | E7 | 207143 | Alico Road Water Main Relocation/Metro Pkwy Ext | 3 |  | Delete project | E | 0 | 11517 | 1740893 | 194358 | 0 | 0 | 0 | 0 | 0 | 0 | 1946768 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1946768
89 | C6 |  | Bayshore Rd 24" WM-Samville to N. Tamiami | 5 |  | Proposed | E | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3450000 | 3450000
90 | E7 | 207334 | Ben Hill Griffin Force Main Improve South | 5 |  | Proposed | E | [8 empty] | 0 | 0 | 0 | 425000 | -425000 | 0 | [5 empty] | 0 | 0 | 0 |  | 450000 | 250000 | 4950000 | 0 | 0 | 5650000 | 0 | 5650000
91 | E7 | 207306 | Ben Hill Griffin Parallel Forcemain | 3 |  | Design NTP 5-8-13 | E |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 290830 | 340961 | 631791 | 0 | 2007747 | 2007747 | [5 empty] | 2007747 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2639538
92 | B6 | 207144 | Bus 41 Line Upgrade-Littleton/Shell Factory | 3 |  | Construction bid awarded | E | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 396632 | 571627 | 968259 | 0 | 28646 | 28646 | [5 empty] | 28646 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 996905
93 | C7 |  | Colonial 30" Water Main-Ortiz to Gumnnery | 5 |  | Proposed | E | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 8400000 | 8400000
94 | F7 |  | Corkscrew Aerator Improvements | 1 |  | Delete project | E | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 |  | 207622 | Corkscrew Exp Prod Well Panel Replace |  |  | Proposed | E | [9 empty] | 0 | 0 | 1170240 | 0 | 1170240 | [5 empty] | 1170240 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1170240
92 |  |  | Corkscrew Groundwater ASR System |  |  | Proposed | E | [9 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 21970000 | 21970000
93 |  |  | Corkscrew Production Well Panal Rep |  |  | Proposed | E | [9 empty] | 0 | 0 | 200000 | 0 | 200000 | [5 empty] | 200000 | 0 | 0 |  | 1250000 | 0 | 0 | 0 | 0 | 1250000 | 0 | 1450000
94 | E8 | 207159 | Corkscrew Rd - Ben Hill to the Habitat | 2 |  | Delete project | E | 11157 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 11157 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11157
95 | F7 | 207158 | Corkscrew Road & I-75 Interchange | 5 |  | Proposed | E | 30716 | 4215 | 8973 | 0 | 0 | 5523 | 7278 | 0 | 0 | 0 | 56705 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56705
96 | E8 |  | Corkscrew WTP Expansion to 20 MGD | 5 |  | Delete project | D | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | E8 |  | Corkscrew WTP Wellfield Improvements | F |  | Delete project | D | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | E8 | 207097 | Corkscrew WTP Wellfield-Alico Road | F3 |  | Complete | E | 833750 | 2197168 | 926908 | 10773695 | 1578462 | 54302 | 791652 | 2800 | 3000 | 2950 | 17164687 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17164687 |  |  | 08/09 | 53500
99 | E8 |  | County 951 Utility Relocation | 4 |  | cancelled 15/16 | E | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 | CW | 207448 | County-Wide Fiber Network | 1 |  | Contract with Century Link | E | [7 empty] | 0 | 88510 | 172788 | 261298 | 100000 | 88702 | 188702 | [5 empty] | 188702 | 0 | 0 |  | 100000 | 50000 | 50000 | 25000 | 25000 | 250000 | 100000 | 800000
101 | D6 |  | Customer Service Center Expansion | 3 |  | Proposed | E | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 | D7 | 207146 | Daniels Parkway & I-75 Interchange | 3 |  | Proposed | E | 500 | 63999 | 3151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67650 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67650
103 | D7 | 207605 | Daniels Parkway Widening-Chamb/Gateway | 3 |  | Complete | E | 0 |  | 0 | 0 | 0 | 59830 | 543014 | 0 | 0 | 0 | 602844 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 602844
104 | D7 | 207307 | Daniels Pkwy Force Main Ext to Gateway | 5 |  | Construct & easement acq deferred | E |  |  |  | 0 | 0 | 42503 | 144515 | 15878 | 1675 | 0 | 204571 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2250000 | 2454571
105 | E5 |  | Deep Injection Well - #2 | 5 | OBJ 54.1 | Proposed | E | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 400000 | 0 | 6000000 | 6400000 | 0 | 6400000
106 | A5 | 207606 | Del Prado Water Main Replacement | 3 |  | Proposed | E | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 200000 | 1075000 | 0 | 0 | 0 | 1275000 | 0 | 1275000
107 | CW | 207416 | DOT Project Utility Relocations | 3 |  | Ongoing | E | 509542 | 354823 | 13105 | 368506 | 340282 | 334484 | 213047 | 326053 | 54111 | 6230 | 2520183 | 0 | 147078 | 147078 | [5 empty] | 147078 | 0 | 0 |  | 100000 | 0 | 0 | 0 | 0 | 100000 | 0 | 2767261
108 | CW | 207429 | Electrical Equipment Upgrades & Replacements | 3 |  | Ongoing | E | 314042 | 174091 | 168057 | 132422 | 567577 | 180315 | 640281 | 575575 | 108256 | 208452 | 3069068 | 536100 | 202619 | 738719 | [5 empty] | 738719 | 0 | 0 |  | 510400 | 233800 | 120000 | 70000 | 70000 | 1004200 | 3300000 | 8111987
109 | D6 | 207449 | Electrical System / Maintenance Building | 5 |  | Pricing construction | E |  |  |  | 0 | 0 | 0 | 0 | 0 | 386 | 15325 | 15711 | 0 | 437289 | 437289 | [5 empty] | 437289 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 453000
110 | CW | 207446 | Energy Management Initiatives Program | NR |  | Ongoing | E | [5 empty] | 0 | 54065 | 135695 | 34134 | 85181 | 309075 | 100079 | 32869 | 132948 | [5 empty] | 132948 | 0 | 0 |  | 100000 | 100000 | 100000 | 25000 | 25000 | 350000 | 100000 | 892023
111 | E5, F5 | 207326 | Estero Blvd Force Main Relocation | 3 |  | Coordinating with LCDOT | E |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 19595 | 19595 | 150000 | 1011394 | 1161394 | [5 empty] | 1161394 | 0 | 0 |  | 1450000 | 150000 | 1450000 | 150000 | 1450000 | 4650000 | 1725000 | 7555989
112 | CW | 207447 | Facility Wide Security System | 2 |  | Ongoing | E | [6 empty] | 0 | 3292 | 18051 | 23089 | 44432 | 25000 | 48155 | 73155 | [5 empty] | 73155 | 0 | 0 |  | 75000 | 75000 | 25000 | 25000 | 25000 | 225000 | 175000 | 517587
113 | E7 | 207304 | FGCU Sewer | 4 |  | FGCU offsite - 30% design | E |  |  | 0 | 0 | 0 | 57420 | 24812 | 59143 | 118805 | 32340 | 292520 | 300000 | 3267146 | 3567146 | [5 empty] | 3567146 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3859666
114 | E7 | 207197 | FGCU Water | 4 |  | FGCU offsite - 30% design | E |  |  | 0 | 13 | 162843 | 235089 | 9626 | 19904 | 25949 | 19185 | 472609 | 275000 | 1245367 | 1520367 | [5 empty] | 1520367 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1992976
115 | E7 | 207292 | FGCU/Miromar Reuse Extension | 5 |  | cancelled 15/16 | E | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
116 | CW | 207613 | Fiber Optic Upgrades | 3 |  | Construction underway | E |  |  |  |  | 0 | 0 | 0 | 76601 | 206033 | 105690 | 388324 | 0 | 626341 | 626341 | [5 empty] | 626341 | 0 | 0 |  | 2900000 | 0 | 0 | 0 | 0 | 2900000 | 0 | 3914665
117 | D5 |  | Fiesta Village Expansion to 6.0 MGD | 5 |  | Delete project | E |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
118 |  |  | Fiesta Village I/O Module Replacement |  |  | Proposed | E | [9 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
119 | D5 | 207293 | Fiesta Village Sewer Collection System Improve | 5 |  | Proposed | E | 0 | 108 | 5826 | 31578 | 0 | 0 | 0 | 0 | 0 | 0 | 37512 | 650000 | -650000 | 0 | [5 empty] | 0 | 0 | 0 |  | 150000 | 950000 | 0 | 0 | 0 | 1100000 | 0 | 1137512
119 |  |  | Fiesta Village WWTP Control Sys Upgrade |  |  |  | E | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | 0 | 0 |  | 100000 | 850000 | 0 | 0 | 0 | 950000 | 0 | 950000
120 | D5 | 207327 | Fiesta Village WWTP Headworks Rehab | 3 |  | 99% design | E | [5 empty] | 0 | 0 | 34554 | 102196 | 190 | 136940 | 0 | 2109375 | 2109375 | [5 empty] | 2109375 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2246315
121 | D5 |  | Fiesta Village WWTP RM Upgrade | 3 |  | Proposed | E | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 300000 | 100000 | 4325000 | 0 | 4725000 | 0 | 4725000
122 |  |  | Fiesta Village WWTP Deep Injection Well |  |  |  | E | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 462500 | 6900000 | 0 | 0 | 0 | 7362500 | 0 | 7362500
123 | D5 | 207450 | Fiesta WWTP Sludge Handling | 1 |  | Proposed | E | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 850000 | -850000 | 0 | [5 empty] | 0 | 0 | 0 |  | 150000 | 950000 | 0 | 0 | 0 | 1100000 | 0 | 1100000
124 | D5 | 207333 | Fiesta Village Switchgear/Generator Repl | 3 |  | Preparing for bid | E | [5 empty] | 0 | 0 | 2010 | 102413 | 302845 | 407268 | 0 | 2865714 | 2865714 | [5 empty] | 2865714 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3272982
125 |  | NEW | FMB Main Switchgear Replacement |  |  | Proposed | E | [9 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 232000 | 1542000 | 0 | 0 | 1774000 | 0 | 1774000
126 | E5 |  | FMB Second Equalization Tank | 5 |  | Delete project | E |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
127 | E5 | 207330 | FMB WWTP Blower Efficiency Improvements | 3 |  | cancelled 15/16 | E | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
128 | E5 | 207451 | FMB WWTP Controls System Replacement | 3 |  | Proposed | E | [8 empty] | 0 | 0 | 0 | 0 | 600000 | 600000 | [5 empty] | 600000 | 0 | 0 |  | 700000 | 0 | 0 | 0 | 0 | 700000 | 0 | 1300000
129 | E5 | 207318 | FMB WWTP EQ Tank Rehabilitation | 3 |  | Complete | E | [5 empty] | 0 | 27940 | 725711 | 7322 | 0 | 760973 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 760973
130 | E5 |  | FMB WWTP EQ Tank Replacement | 3 |  | Proposed | E | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 480000 | 8200000 | 0 | 8680000 | 0 | 8680000
131 | CW | 207313 | Force Main Replacements | 3 |  | Complete | E |  |  |  |  | 0 | 257582 | 177739 | 369125 | 0 | 0 | 804446 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 804446
132 | D5 | 207270 | Force Main to PS 393 Replacement | 3 |  | Delete project | E |  |  |  | 0 | 0 | 0 | 0 | 0 | 26086 | 0 | 26086 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26086
133 | D7 | 207452 | Gateway Operations Building/Sludge Cover | 3 |  | Proposed | E | [7 empty] | 0 | 0 | 2538 | 2538 | 0 | 317462 | 317462 | [5 empty] | 317462 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000
134 | D7 | 207308 | Gateway WWTP ASR Well System | 3 |  | cancelled 15/16 | E |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
135 | D7 | 207323 | Gateway WWTP - Davco Rehab | 3 |  | Advertise for construction - 4th Qtr | E | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2250000 | 2250000 | [5 empty] | 2250000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250000
136 |  |  | Gateway WWTP Sludge Dewatering System Roof |  |  | Proposed | E | [20 empty] | 0 | 0 |  | 0 | 65000 | 0 | 0 | 0 | 65000 | 0 | 65000
137 | D5 | 207431 | Gladiolus W/S Relocation-Pine Ridge to Winkler | 3 |  | Construction 95% complete | E | 85438 | 33499 | 8549 | 813324 | 1609263 | 392467 | 939256 | 62316 | 403705 | 143 | 4347960 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4347960
138 | E7 | 207187 | Green Meadow WTP Expansion | 5 |  | Advertise RFQ for Construct Manager | E, D | 0 |  | 239760 | 1048698 | 54712 | 686803 | 882668 | 1119045 | 751108 | 655038 | 5437832 | 11000000 | 60359534 | 71359534 | [5 empty] | 71359534 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76797366
139 | B7 |  | High Point WWTP Diversion to FGUA | 3 |  | Delete project | E | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
140 | CW | 207247 | Inflow & Infiltration Improvement | 3 |  | Ongoing | E | 1175459 | 179309 | 238543 | 670947 | 704876 | 1569487 | 1342580 | 427224 | 1354610 | 455689 | 8118724 | 500000 | 239892 | 739892 | [5 empty] | 739892 | 0 | 0 |  | 500000 | 500000 | 500000 | 500000 | 500000 | 2500000 | 2000000 | 13358616
141 | CW | 207430 | Instrumentation Upgrades & Improvements | 3 |  | Proposed | E | 666455 | 184929 | 86731 | 10467 | 183361 | 152678 | 129714 | 78521 | 0 | 92594 | 1585450 | 115100 | 6110 | 121210 | [5 empty] | 121210 | 0 | 0 |  | 202500 | 150000 | 150000 | 100000 | 100000 | 702500 | 600000 | 3009160
142 | E7 |  | Interconnect Pinewoods Distribution Sys | 3 |  | Proposed | E | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 4850000 | 4850000
143 | CW | 207444 | LCU Generator Replace & Improve | 3 |  | Ongoing | E |  |  |  | 0 | 0 | 14405 | 67963 | 638269 | 100335 | 391268 | 1212240 | 340000 | 19185 | 359185 | [5 empty] | 359185 | 0 | 0 |  | 348000 | 198000 | 0 | 0 | 0 | 546000 | 1000000 | 3117425
144 | CW | 207190 | Lime Sludge Handling Facilities Improvements | 3 |  | cancelled 15/16 | E |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
145 |  |  | Mariana Ave WM Replacement |  |  | Proposed | E | [10 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 60000 | 500000 | 0 | 0 | 0 | 560000 | 0 | 560000
146 |  | 207335 | Master Lift Station 7716 Improvements |  |  | Proposed | E | [9 empty] | 0 | 0 | 800000 | -800000 | 0 | [5 empty] | 0 | 0 | 0 |  | 825000 | 1425000 | 0 | 0 | 0 | 2250000 | 0 | 2250000
147 | E5 | 207252 | Matanzas Pass Force Main | 4 |  | Proposed | E | 196813 | 1210955 | 30057 | 355407 | 1226525 | 323308 | 0 | 0 | 0 | 0 | 3343065 | 0 | 130000 | 130000 | [5 empty] | 130000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3473065
148 |  |  | McGregor-Tanglewood Force Main Rep |  |  | Proposed | R | [10 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 440000 | 2900000 | 0 | 0 | 3340000 | 0 | 3340000
149 | D5 | 207453 | McGregor Blvd Water Main Replacement | 3 |  | Proposed | E | [7 empty] | 0 | 0 | 0 | 0 | 2000000 | 900000 | 2900000 | [5 empty] | 2900000 | 0 | 0 |  | 4000000 | 0 | 0 | 0 | 0 | 4000000 | 0 | 6900000
150 | B5 | 207611 | N Cleveland Water Main Replacement | 3 |  | Design 30% Complete | E | [6 empty] | 0 | 465 | 67095 | 84785 | 152345 | 750000 | 386152 | 1136152 | [5 empty] | 1136152 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1288497
151 | B7 | 207618 | NLC WTP Deep Injection Well Backup | 3 |  | Proposed | E | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 425000 | 5350000 | 0 | 0 | 5775000 | 0 | 5775000
152 | A7 | 207602 | North Lee County RO Plant Wellfield Expansion | 5 |  | Phase 2B Construction 80% Comp | E |  |  | 0 | 550678 | 4789639 | 1699581 | 3336907 | 1728562 | 3354289 | 325061 | 15784717 | 0 | 1018584 | 1018584 | [5 empty] | 1018584 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16803301 |  |  | 08/09 | 6500
153 | A7 | 207028 | North Lee County WTP Expansion to 10 MGD | 5 |  | Complete | E | 0 |  | 2640 | 6838 | 0 | 4230512 | 13407160 | 151133 | 90449 | 0 | 17888732 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17888732 | 10/11 | 40000 | 10/11 | 975000
154 | A7 |  | North Lee County WTP Expansion to 15 MGD | 5 |  | Proposed | E | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 2300000 | 0 | 2300000 | 28300000 | 30600000
155 | A7 | 207619 | NLC WTP Wellfield Expansion to 15 MGD | 5 |  | Proposed | E | [8 empty] | 0 | 1013 | 1013 | 0 | 250000 | 250000 | [5 empty] | 250000 | 0 | 0 |  | 0 | 0 | 0 | 2618986 | 0 | 2618986 | 10580000 | 13449999
156 | C7,D7 |  | North-South 30" Water Main-SR80 to AHR | 3,5 |  | Proposed | E | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 28200000 | 28200000
157 | B5.B6 |  | N Tamiami 24" WM-Pondella to Cleveland | 5 |  | Proposed | E | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 5600000 | 5600000
158 | B8 | 207311 | Olga WTP Alternative Water Source & Process Imp. | 3 |  | Proposed | E |  |  |  | 0 | 195635 | 580391 | 59707 | 0 | 0 | 0 | 835733 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 835733
158 |  |  | Olga WTP MCC Replacement |  |  | Proposed | E | [9 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 500000 | 500000 | 0 | 0 | 0 | 1000000 | 0 | 1000000
159 | B8 | 207265 | Olga WTP Reservoir & Plant Improvements | 1 |  | In final design | E | 515569 | 861184 | 3561365 | 773746 | 111907 | 455631 | 1087390 | 533445 | 65372 | 64174 | 8029783 | 0 | 1240419 | 1240419 | [5 empty] | 1240419 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9270202 |  |  | 12/13 | 150000
160 | B6 | 207454 | Operations Building Replacement | 3 |  | Proposed | E | [8 empty] | 0 | 0 | 0 | 150000 | -150000 | 0 | [5 empty] | 0 | 0 | 0 | 75000 | 75000 | 0 | 0 | 0 | 0 | 75000 | 2500000 | 2575000
161 | B5 |  | Orange Grove WM-Pondella to Hancock | 3 |  | Proposed | E | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 100000 | 700000 | 0 | 0 | 800000 | 0 | 800000
162 | B7 |  | Ortiz FM - Palm Beach to Ballard | 3 |  | Proposed | E | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2150000 | 2150000
163 | B7 |  | Ortiz Ave Utility Relocation-MLK to SR80 | 3 |  | Proposed | E | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 6000000 | 6000000
164 | C6 | 207161 | Ortiz Ave Water Relocation-Colonial to SR 80 | 3 |  | Delete project | E | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
165 | D6 | 207127 | Page Park Waterline Improvements | 3 |  | Consultant NTP on 7-10-13 | E | 0 |  | 0 | 9287 | 0 | 0 | 0 | 0 | 58487 | 154209 | 221983 | 1300000 | 443784 | 1743784 | [5 empty] | 1743784 | 0 | 0 |  | 4100000 | 0 | 0 | 0 | 0 | 4100000 | 0 | 6065767
166 | B7 | 207328 | Palm Beach Blvd FM at Orange River | 1 |  | Design 30% complete | E | [5 empty] | 0 | 0 | 0 | 74748 | 41403 | 116151 | 0 | 1050975 | 1050975 | [5 empty] | 1050975 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1167126
167 | D3 | 207331 | Pine Island Operations Building | 3 |  | RFP for Design Build | E | [7 empty] | 0 | 2042 | 145092 | 147134 | 0 | 128433 | 128433 | [5 empty] | 128433 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275567
168 | D3 | 207238 | Pine Island Sewer Transmission System | 5 |  | Proposed | E | 27767 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 27767 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4027767
169 | D3 | 207332 | Pine Island WWTP Barscreen | 3 |  | RFP for Design Build | E | [7 empty] | 0 | 1342 | 195713 | 197055 | 0 | 152843 | 152843 | [5 empty] | 152843 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 349898
170 | D3 | 207239 | Pine Island WWTP Expansion | 5 |  | Proposed | E | 403481 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 403481 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 6500000 | 6903481
171 |  | 207336 | Pine Island WWTP Tank Rehab |  |  | Proposed | E | [9 empty] | 0 | 0 | 580000 | 0 | 580000 | [5 empty] | 580000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 580000
172 |  | NEW | Pine Ridge FM-FMB WWTP/Gulf Reflections |  |  | Proposed | E | [9 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 230000 | 200000 | 1533000 | 0 | 0 | 1963000 | 0 | 1963000
173 |  | 207321 | Pine Ridge FM-San Carlos to FMBWWTP | 1 |  | Complete | E | [5 empty] | 0 | 550 | 13889 | 1363599 | 16363 | 1394401 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1394401
174 | F7 | 207615 | Pinewoods Chemical Tank Replacements | 3 |  | Design 30% Complete | E | [7 empty] | 0 | 27204 | 36609 | 63813 | 0 | 517116 | 517116 | [5 empty] | 517116 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 580929
175 | F7 |  | Pinewoods Odor Control Scrubber | 3 |  | Proposed | E | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 200000 | 0 | 0 | 0 | 200000 | 0 | 200000
176 | F7 | 207607 | Pinewoods Wellfield Electrical Improvements | 3 |  | Modeling underway | E |  |  |  |  | 0 | 0 | 63855 | 91730 | 70533 | 20802 | 246920 | 0 | 4304964 | 4304964 | [5 empty] | 4304964 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4551884
177 | F7 | 207608 | Pinewoods WTP Deep Injection Well (Mods) | 3 |  | Consultant selection underway | E | [5 empty] | 0 | 16000 | 3500 | 0 | 87005 | 106505 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106505
178 | F7 |  | Pinewoods WTP Degasifiers Replacement | 3 |  | Proposed | E | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 759000 | 0 | 0 | 0 | 759000 | 0 | 759000
179 | D5 | 207284 | Reclaim Water ASR | 5 |  | Proposed | E | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 1260000 | 0 | 4500000 | 0 | 0 | 5760000 | 0 | 5760000
180 | CW | 207289 | Regional Sludge Handling Plant | 5 |  | Proposed | E | 13727 | 164192 | 160522 | 79886 | 0 | 0 | 0 | 0 | 0 | 0 | 418327 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 418327
181 | CW | 207324 | Regional WWTP Study | 5 |  | cancelled 15/16 | E | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
182 | CW | 207455 | Reuse System & Site Improvements | 3 |  | Proposed | E | [8 empty] | 0 | 57160 | 57160 | 0 | 447645 | 447645 | [5 empty] | 447645 | 0 | 0 |  | 0 | 1500000 | 1500000 | 0 | 0 | 3000000 | 0 | 3504805
183 | E7 | 207162 | San Carlos Blvd Improv-Linda Loma to Kelly | 3 |  | Proposed | E | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1800000 | 1800000
184 | E5 | 207320 | San Carlos FM - Main to Hurricane Pass | 1 |  | Emergency construction complete | E | [5 empty] | 0 | 26063 | 61543 | 414952 | 0 | 502558 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 502558
185 | E7 | 207329 | San Carlos WWTP Diversion to 3 Oaks WWTP | 3 |  | Design 10% Complete | E |  |  |  | 0 |  | 0 | 0 | 0 | 44844 | 41679 | 86523 | 0 | 673769 | 673769 | [5 empty] | 673769 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 760292
186 | CW | 207424 | SCADA Upgrades & Improvements | 3 |  | Ongoing | E | 586870 | 223717 | 170815 | 222618 | 307965 | 7668 | 164024 | 181483 | 249714 | 556144 | 2671018 | 700000 | 405674 | 1105674 | [5 empty] | 1105674 | 0 | 0 |  | 400000 | 400000 | 300000 | 200000 | 200000 | 1500000 | 1500000 | 6776692
187 | CW | 207456 | Secondary Containments-Chemical Tanks | 3 |  | Proposed | E | [8 empty] | 0 | 38048 | 38048 | 0 | 144313 | 144313 | [5 empty] | 144313 | 0 | 0 |  | 150000 | 150000 | 150000 | 400000 | 0 | 850000 | 0 | 1032361
188 | CW | 207198 | SFM Water Storage Tanks | 5 |  | Delete project | E |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
189 | CW | 207184 | SFM Water Transmission Line Improvements | 5 |  | Construction deferred | E | 0 |  | 0 | 132553 | 110241 | 16077 | 29635 | 41454 | 0 | 0 | 329960 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 200000 | 2000000 | 2200000 | 0 | 2529960
190 | B6 | 207199 | SR 80 & I-75 Water Relocation | 5 |  | Construction 97% Complete | E |  |  | 0 | 0 | 0 | 255127 | 118952 | 110279 | 24272 | 4511 | 513141 | 0 | 144281 | 144281 | [5 empty] | 144281 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 657422
191 | C6 | 207425 | Summerlin Rd-Boy Scout to University W/S Relocation | 3 |  | Legal issues pending | E | 41851 | 8309 | -800 | 1294027 | 422375 | 12464 | 0 | 0 | 0 | 0 | 1778226 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1778226
192 | C6 | 207194 | Summerlin Road Water System Improvements | 5 |  | Proposed | E | 0 |  | 0 | 34752 | 343135 | 99179 | 29275 | 13181 | 0 | 0 | 519522 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 6379248 | 6898770
193 | E7 | 207325 | Three Oaks Oxidation Ditch Improvements | 4 |  | NTP evaluation phase | E | [6 empty] | 0 | 0 | 77422 | 564631 | 642053 | 17000000 | 1330002 | 18330002 | [5 empty] | 18330002 | 0 | 0 |  | 24000000 | 0 | 0 | 0 | 0 | 24000000 | 0 | 42972055
194 | E7 | 207301 | Three Oaks Reuse System Augmentation | 3 |  | Completing FDEP & D.O. permits | E |  |  |  |  | 8480 | 20013 | 108047 | 46905 | 17197 | 2815812 | 3016454 | 0 | 391095 | 391095 | [5 empty] | 391095 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3407549
195 | E7 |  | Three Oaks WWTP Expansion to 8 MGD | 5 |  | Proposed | E | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 28000000 | 28000000
196 | B7 | 207164 | Tice Street Loop | 3 |  | Design STA approved | E | 0 |  |  |  | 0 | 0 | 0 | 0 | 56225 | 31249 | 87474 | 0 | 13065 | 13065 | [5 empty] | 13065 | 0 | 0 |  | 900000 | 0 | 0 | 0 | 0 | 900000 | 0 | 1000539
197 | D7 |  | Treeline WM-Terminal Access to Daniels | 5 |  | Proposed | E | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 4430000 | 4430000
198 | B6 | 207617 | US 41/Palm Ave WM - Betmar to Hancock | 3 |  | Construction 90% complete | E | [5 empty] | 0 | 0 | 0 | 826400 | 0 | 826400 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 826400
199 | B5 | 207610 | US 41 Util Reloc-Corkscrew to San Carlos | 3 |  | Complete | E | [5 empty] | 0 | 329927 | 51853 | 103127 | 0 | 484907 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 484907
200 | B5 | 207170 | US 41 Watermain Improvement | 3 |  | Construction 70% complete | E | 0 |  | 0 | 0 | 0 | 0 | 0 | 217967 | 1397271 | 293295 | 1908533 | 3800000 |  | 3800000 | [5 empty] | 3800000 | 0 | 0 |  | 2500000 | 0 | 0 | 0 | 0 | 2500000 | 0 | 8208533
201 | CW | 207229 | Wastewater System Improvements | 3 |  | Ongoing | E | 479528 | 468821 | 196524 | 85350 | 172861 | 242399 | 237657 | 225803 | 229409 | 335737 | 2674089 | 250000 | 1327 | 251327 | [5 empty] | 251327 | 0 | 0 |  | 250000 | 250000 | 250000 | 250000 | 250000 | 1250000 | 1000000 | 5175416
202 | CW | 207138 | Wastewater Treatment Plant Improvements | 1 |  | Ongoing | E | 1125126 | 171618 | 213466 | 488549 | 221710 | 35460 | 943665 | 115298 | 93393 | 566110 | 3974395 | 380000 | 533776 | 913776 | [5 empty] | 913776 | 0 | 0 |  | 370000 | 245000 | 500000 | 0 | 0 | 1115000 | 2900000 | 8903171
203 | CW | 207609 | Water Bacteriological Sampling Stations | 1 |  | Completed | E | [5 empty] | 0 | 250133 | 356864 | 0 | 0 | 606997 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 606997
204 | CW | 207094 | Water System Improvements | 3 |  | Installing waterlines - San Carlos Park | E | 523350 | 127468 | 10190 | 56792 | 283756 | 951690 | 483900 | 457779 | 575264 | 509225 | 3979414 | 250000 | 283522 | 533522 | [5 empty] | 533522 | 0 | 0 |  | 500000 | 500000 | 500000 | 500000 | 500000 | 2500000 | 1000000 | 8012936
205 | D7 | 207193 | Water Transmission Ben Hill To Treeline | 5 |  | Construction Deferred | E | 0 | 39031 | 2491114 | 249191 | 288202 | 19465 | 82460 | 7936 | 45477 | 131874 | 3354750 | 0 | 179607 | 179607 | [5 empty] | 179607 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 6960000 | 10494357
206 | CW | 207086 | Water Transmission System Improvements | 5 |  | Pending Final Acceptance | E | 1551168 | 51028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1602196 | 0 | 645414 | 645414 | [5 empty] | 645414 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2247610
207 | CW | 207268 | Water Treatment Plant Improvements | 1 |  | Ongoing | E | 837185 | 429675 | 287247 | 248580 | 78439 | 1159839 | 1551050 | 661203 | 163138 | 394560 | 5810916 | 180600 | 306069 | 486669 | [5 empty] | 486669 | 0 | 0 |  | 90000 | 0 | 0 | 0 | 0 | 90000 | 0 | 6387585
208 | E7 | 207426 | Water/Sewer Line Relocation-Three Oaks Ext. | 3 |  | Proposed | E | 250 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 300500
209 | CW | 207149 | Well Redevelopment/Upgrade & Rebuild | 3,5 |  | Ongoing | E | 678714 | 79716 | 232330 | 597002 | 760980 | 611615 | 562164 | 256663 | 302838 | 385 | 4082407 | 130000 | 404081 | 534081 | [5 empty] | 534081 | 0 | 0 |  | 130000 | 130000 | 130000 | 130000 | 130000 | 650000 | 710000 | 5976488
210 |  | NEW | Winkler Road Watermain Improvement |  |  | Proposed | E | [9 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 200000 | 2100000 | 0 | 0 | 0 | 2300000 | 0 | 2300000
211 | C5 | 207183 | Waterway Esatates Water Transmission Line Imp | 5 |  | Proposed | E | 0 |  | 72350 | 119076 | 11669 | 12050 | 28144 | 10835 | 0 | 0 | 254124 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 150000 | 1100000 | 0 | 0 | 1250000 | 0 | 1504124
212 | C5 | 207315 | Waterway Estates WWTP Flow Diversion | 3 |  | cancelled 15/16 | E |  |  |  |  | 0 | 0 | 4508678 | 2505751 | 838914 | 0 | 7853343 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7853343
213 | CW | 207274 | WWTP Odor Control System Improvements | 3 |  | cancelled 15/16 | E | 6324 |  | 0 | 46382 | 316008 | 0 | 0 | 92617 | 78616 | 3003 | 542950 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
214 | C6 | 207620 | Work Dr Industrial Pk WM Improvements | 3,4 |  | Proposed | E | [8 empty] | 0 | 0 | 0 | 2075000 | 0 | 2075000 | [5 empty] | 2075000 | 0 | 0 |  | 600000 | 2000000 | 0 | 0 | 0 | 2600000 | 0 | 4675000
215 | B6 | 207621 | Yacht Club Colony Distribution Sys Rehab | 1 |  | Proposed | E | [8 empty] | 191 | 175591 | 175782 | 0 | 2582941 | 2582941 | [5 empty] | 2582941 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2758723
216 |  |  | UTILITIES CAPITAL TOTAL |  |  |  |  | 10614782 | 7039622 | 10868316 | 19394722 | 14850903 | 14775357 | 33421493 | 12609854 | 14907971 | 11198458 | 149681478 | 47082119 | 94241796 | 141323915 | 0 | 0 | 0 | 0 | 0 | 141323915 | 0 | 0 |  | 50888400 | 25002800 | 33030000 | 20018986 | 11275000 | 140215186 | 198729248 | 629406877
217
218 |  |  | SOLID WASTE
219
220 | G7 | 200939 | Electric System Improvements | 3 |  | Proposed | E | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 750000 | [5 empty] | 750000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000
221 | C7 | 200928 | Household Chemical Facility | 1 | Pol 62.1.2 | Complete | E | 25089 | 21571 | 2063048 | 653347 | 15079 | 23967 | 9559 | 11017 | 7527 | 0 | 2830204 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2830204
222 | C7 | NEW | Household Chemical Facility |  |  | Proposed | E | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 500000 | 3500000 | 0 | 0 | 4000000 | 0 | 4000000 | 17/18 | 100000 | 18/19 | 500000
223 |  | NEW | LaBelle Transfer Station Expansion |  |  | Proposed | E | [9 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 1000000 | 3500000 | 0 | 4500000 | 0 | 4500000
224 | D10 | 200936 | Landfill Gas Collection System | NR |  | Reviewing Regulatory Requirements | E |  |  | 0 | 16906 | 0 | 0 | 0 | 0 | 0 | 0 | 16906 | 3250000 | 0 | 3250000 | [5 empty] | 3250000 | 0 | 0 |  | 0 | 0 | 250000 | 300000 | 0 | 550000 | 2000000 | 5816906
225 | D10 | 200937 | Lee Hendry Landfill Expansion 2014 | 5 |  | Cancelled | E |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 607330 | 7526723 | 8134053 | 0 | 10675642 | 10675642 | [5 empty] | 7565947 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15700000
226 | D10 | NEW | Lee Hendry Landfill Expansion 2022 | 5 |  | Cancelled | E |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 607330 | 7526723 |  | 0 | 10675642 | 10675642 | [6 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 12000000 | 12000000
227 | D10 | 200931 | Lee Hendry Landfill Leachate Treatment | 1 | Pol 62.1.2 | Complete | E | 0 |  | 0 | 36346 | 149878 | 482407 | 4283037 | 234276 | 6456 | 0 | 5192400 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5192400
228 | C7 | 200933 | MRF Expansion | 5 | Pol 62.1.2 | Construction - 98% | E | 0 |  | 0 | 166795 | 1032391 | 5529552 | 1238222 | 171859 | 979916 | -1302 | 9117433 | 0 | 132567 | 132567 | [5 empty] | 132567 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9250000 | 11/12 | 25000 | 11/12 | 50000
229 | G7 | 200940 | Scale Improvements | 5 |  | Proposed | E | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 450000 | 450000 | 900000 | [5 empty] | 900000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000
230 | C7 | NEW | Recycling Facility (name change) |  |  | Proposed | E | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 250000 | 7500000 | 15000000 | 0 | 0 | 22750000 | 0 | 22750000 | 18/19 | 250000 | 19/20 | 250000
231 | C7 | NEW | Waste to Energy |  |  | Proposed | E-debt | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 400000 | 3000000 | 12000000 | 200000000 | 100000000 | 315400000 | 0 | 315400000
230 | C7 | 200923 | Solid Waste Processing Equipment | F | Pol 62.1.2 | Construction - 99% | E,D | 18934577 | 59989066 | 35459213 | 5551499 | 1353570 | 5104407 | 3026239 | 266205 | 861667 | 387195 | 130933638 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130933638
231 |  |  | SOLID WASTE CAPITAL TOTAL |  |  |  |  | 18959666 | 60010637 | 37522261 | 6424893 | 2550918 | 11140333 | 8557057 | 683357 | 3070226 | 15439339 | 156224634 | 3700000 | 22683851 | 26383851 | 0 | 0 | 0 | 0 | 0 | 12598514 | 0 | 0 |  | 650000 | 11000000 | 31750000 | 203800000 | 100000000 | 347200000 | 14000000 | 530023148
232
233 |  |  | COUNTY LANDS
234
235 | CW | 208800 | Conservation 2020 |  | Pol 107.1.1 | 2,981 acres under negotiations | A | 87084171 | 3253242 | 44330623 | 35586505 | 45598253 | 34296389 | 10930785 | 3244200 | 171772 | 3170473 | 267666413 | 0 | 62946378 | 62946378 | [5 empty] | 62946378 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330612791
236 |  |  | COUNTY LANDS CAPITAL TOTAL |  |  |  |  | 87084171 | 3253242 | 44330623 | 35586505 | 45598253 | 34296389 | 10930785 | 3244200 | 171772 | 3170473 | 267666413 | 0 | 62946378 | 62946378 | 0 | 0 | 0 | 0 | 0 | 62946378 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330612791
237
238 |  |  | GOVERNMENT FACILITIES
239
240 | D6 | 208838 | Animal Shelter Expansion | 5 |  | Complete | A |  |  |  | 0 | 105710 | 1137644 | 1472447 | 99635 | 19154 | 0 | 2834590 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2834590 |  |  | 09/10 | 7200
241 | E5 | 203414 | Beach Park & Ride | 5 |  | Acquire Parcel in FY 12-13 | A, G48640 | 0 |  | 0 | 0 | 13200 | 11800 | 0 | 0 | 14650 | 49775 | 89425 | 2243484 | 2564827 | 4808311 | [5 empty] | 4808311 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4897736
242 | C5,D5 | 208904 | Bus Rapid Transit | 5 |  | Proposed | A, G48640 | [7 empty] | 0 | 0 |  | 0 | 300000 | 550000 | 850000 | [5 empty] | 850000 | 0 | 0 |  | 0 | 0 | 0 | 5427000 | 0 | 5427000 | 0 | 6277000
243 | A5 |  | Charlotte County Connector | 5 |  | Proposed | A. G48640 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 5000000 | 5000000 | 0 | 5000000
244 | C6 | 208872 | Edison Mall Transfer Center | 5 |  | Complete | A,E | 0 |  | 35926 | 9720 | 8376 | 42445 | 463250 | 670521 | 57286 | 0 | 1287524 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1287524 |  |  | 12/13 | 212400
245 | C7 | 208666 | Emergency Operations Center | 5 |  | Construction substantially complete | A,G48640, S | 1215 | 227 | 41552 | 37408 | 0 | 930100 | 3092709 | 10055678 | 2376611 | 27901 | 16563401 | 0 | 539244 | 539244 | [5 empty] | 539244 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17102645
246 | CW | 208873 | Fiber Optic Expansion | 5 |  | Ongoing | E | 0 |  | 0 | 38785 | 28874 | 345156 | 5541 | 861053 | 508471 | 93090 | 1880970 | 0 | 745080 | 745080 | [5 empty] | 745080 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2626050 |  |  | 08/09 | 212400
247 | CW | 203415 | Integrated Justice Information System | 5 |  | Ongoing - Court System project | A | [5 empty] | 0 | 223275 | 308120 | 742204 | 349251 | 1622850 | 0 | 211245 | 211245 | [5 empty] | 211245 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1834095
248 | C6 | 208735 | Lee Tran Operations & Maintenance Facility | 5 |  | Construction 20% complete | E, G48640, S | 0 | 395552 | 22582 | 194075 | 29513 | 7942998 | 459341 | 1465287 | 5924638 | 21516395 | 37950381 | 0 | 8349074 | 8349074 | [5 empty] | 8349074 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46299455
249 | C3 | 208836 | New EMS Station - Matlacha | 5 |  | Proposed | A | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2263109 | 2263109
250 | CW | 208894 | Park & Ride/Transit Stations | 3 |  | Ongoing | A, E, G48640 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 136000 | 136000 | [5 empty] | 136000 | 0 | 0 |  | 3000000 | 0 | 0 | 1000000 | 1000000 | 5000000 | 0 | 5136000 | 16/17 | 160000
251 |  |  | Research Diamond Circulator | 5 |  | Delete Project | G48640 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
252 | C6 | NEW | Rosa Parks Intermodal Center Expansion | 5 |  | Proposed | G48640 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 6000000 | 0 | 0 | 6000000 | 0 | 6000000
253 |  | 203416 | Tidemark Permitting Software Replace |  |  | Proposed | S | [9 empty] | 0 | 0 | 1000000 | 0 | 1000000 | [5 empty] | 1000000 | 0 | 0 |  | 1900000 | 0 | 0 | 0 | 0 | 1900000 | 0 | 2900000 |  |  | 16/17 | 50000
253 | CW | 208864 | Transit Passenger Amenities | 1 |  | Shelters built annually at bus stops | A, G48640 | [5 empty] | 0 | 0 | 270271 | 468549 | 507591 | 1246411 | 100000 | 771916 | 871916 | [5 empty] | 871916 | 0 | 0 |  | 500000 | 1000000 | 1000000 | 1000000 | 1000000 | 4500000 | 5000000 | 11618327
254 | CW | NEW | EMS Station 11 Replacement |  |  | Proposed | A | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 195931 | 0 | 0 | 0 | 0 | 195931 | 0 | 195931
255 |  |  | GOVERNMENT FACILITIES CAPITAL TOTAL |  |  |  |  | 1215 | 395779 | 100060 | 279988 | 185673 | 10410143 | 5716563 | 13730565 | 10111563 | 22544003 | 63475552 | 3643484 | 13867386 | 17510870 | 0 | 0 | 0 | 0 | 0 | 17510870 | 0 | 0 | 0 | 5595931 | 1000000 | 7000000 | 7427000 | 7000000 | 28022931 | 7263109 | 116272462
256
257 |  |  | LIBRARY PROJECTS
258
259 | C6 | 203619 | Fort Myers Library | 5 |  | Construction 90% complete | LA | 0 |  | 28895 | 11400 | 380 | 220840 | 673334 | 3881484 | 11168266 | 2509541 | 18494140 | 0 | 500000 | 500000 | [5 empty] | 500000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18994140 | 12/13 | 948350 | 12/13 | 2258728
260 | C6 |  | Fort Myers Library Fresh Air Unit Replacement | 3 |  | Proposed | LA | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
261 |  | 203754 | Pine Island Library Renovation |  |  |  | LA | [9 empty] | 5050 | 5050 | 0 | 168450 | 168450 | [5 empty] | 168450 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173500
262 |  | 203627 | Two Community Libraries |  |  | Proposed | LA | [9 empty] | 0 | 0 | 2000000 | 0 | 2000000 | [5 empty] | 2000000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
|  |  | North Ft Myers Library |  |  | Proposed | LA | [12 empty] | 0 | 0 | [5 empty] | 0 |  |  |  | 11973125 | 0 | 0 | 0 | 0 | 11973125 | 0 | 11973125 | 16/17 | 600000 | 16/17 | 300000
|  |  | Bonita Springs Library |  |  | Proposed | LA | [12 empty] | 0 | 0 | [5 empty] | 0 |  |  |  | 10695625 | 0 | 0 | 0 | 0 | 10695625 | 0 | 10695625 | 16/17 | 600000 | 17/18 | 310000
263 |  |  | LIBRARY CAPITAL TOTAL |  |  |  |  | 0 | 0 | 28895 | 11400 | 380 | 220840 | 673334 | 3881484 | 11168266 | 2514591 | 18499190 | 2000000 | 668450 | 2668450 | 0 | 0 | 0 | 0 | 0 | 2668450 | 0 | 0 |  | 22668750 | 0 | 0 | 0 | 0 | 22668750 | 0 | 21167640
264
265 |  |  | PARKS - COMMUNITY & REGIONAL
266
267 | C6 | 201861 | Adult Soccer Fields | 5 |  | Deleted | A | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
268 | A9 | 202144 | Alva/Olga Improvements | 5 |  | Olga restrooms complete | I-21 | [6 empty] | 0 | 10437 | 32039 | 0 | 42476 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42476 |  |  | 12/13 | 20000
269 | A1 | 201778 | Boca Grande Improvements | NA |  | Equipment to complete fitness room | I-7,27 | 59352 | 943 | 0 | 0 | 0 | 0 | 6704 | 6894 | 0 | 14977 | 88870 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88870
270 | C6 | 202015 | Brooks Park Irrigation/Well System | 3 |  | Deleted | A | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 64628 | 3516 | 68144 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68144
271 | C6 | 202146 | Brooks Park Master Plan & Improvements | 5 |  | Land transfer complete | I-24 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | -95 | 0 | -95 | 0 | 53856 | 53856 | [5 empty] | 53856 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1250000 | 1303761 | 12/13 | 40000 | 12/13 | 22500
272 | A8 | 202153 | Caloosahatchee Reg Pk Maint Building | 3 |  | Proposed | I-R | [8 empty] | 0 | 3400 | 3400 | 0 | 96600 | 96600 | [5 empty] | 96600 | 0 | 0 |  | 250000 | 0 | 0 | 0 | 0 | 250000 | 0 | 350000
273 | C6 | 201870 | City of Palms Improvements | 3 |  | Delete Project | A | 0 |  | 916435 | 67066 | 0 | 0 | 0 | 0 | 0 | 0 | 983501 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 983501
274 | CW | 202154 | Greenways | 5 |  | Proposed | I-R | [7 empty] | 0 | 0 | 0 | 0 | 100000 | 0 | 100000 | [5 empty] | 100000 | 0 | 0 |  | 0 | 150000 | 600000 | 0 | 0 | 750000 | 1150000 | 2000000
275 | C6 | 202145 | Hunter Park Improvements | 5 |  | Signs & benches installed | I-24 | 0 |  | 0 | 0 | 0 | 0 | 0 | 4390 | 0 | 0 | 4390 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4390 |  |  | 12/13 | 20500
276 | B8 |  | Idalia Park | 5 |  | Proposed | I - R | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
277 |  | 201865 | Lehigh Park Acquisition & Improvements | 3 |  | Admiral Lehigh 80% complete | I-23 | [5 empty] | 0 | 98012 | 442874 | 2501796 | 246726 | 3289408 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | 4789408
278 | B6 | 201956 | North Fort Myers Recreation Center | 5 |  | Construction 90% complete | Loan, I-22 |  |  | 0 | 0 | 0 | 79806 | 108999 | 649159 | 7828547 | 1194024 | 9860535 | 0 | 30090 | 30090 | [5 empty] | 30090 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9890625 |  |  | 13/14 | 500000
279 | C7 | 202148 | Orange River Property | NR |  | Ongoing | A | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
280 | C3 | 201798 | Phillips Park | 5 |  | Ongoing improvements | I-5,25 | 3623 | 23101 | 17948 | 91025 | 276520 | 103786 | 76858 | 38275 | 31835 | 27943 | 690914 | 0 | 287025 | 287025 | [5 empty] | 287025 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 977939 |  |  | 09/10 | 50000
281 | B2 |  | Pine Island Comm Marina Mstr Plan & Impr | 3 |  | Proposed | A | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1050000 | 1050000
282 | CW | 201868 | Pool Water Feature Playground | 5 |  | Deleted | A | 0 |  | 31327 | 0 | 37477 | 121624 | 0 | 0 | 0 | 0 | 190428 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190428 |  |  | 08/09 | 33000
283 |  | 202499 | Red Sox Stadium | 5 |  | Construction Complete | D |  | 0 | 0 | 0 | 704685 | 24714847 | 36100583 | 19042731 | 257500 | 0 | 80820346 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80820346
284 | D6 | 201002 | Sports Complex Improvements | 3 |  | Deleted | A | 0 |  | 1030881 | 253703 | 0 | 0 | 0 | 0 | 0 | 0 | 1284584 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1284584
285 | D6 | 202147 | Twins Spring Training Facility Improvements | 5 |  | Design underway | S | [6 empty] | 0 | 238375 | 3768227 | 32454056 | 238375 | 0 | 13228269 | 13228269 | [5 empty] | 13228269 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13466644
285 | D5 | 201873 | Wa-Ke Hatchee Community Park | 5 |  | Construction started pickle ball courts | I-4,24,A,S | 2695003 | 874071 | 576030 | 846538 | 270179 | 3382137 | 967875 | 40431 | 129983 | 61683 | 9843930 | 0 | 7461 | 7461 | [5 empty] | 7461 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9851391
285 | D5 |  | Terry Park Main/Storage Bldg |  |  | Proposed | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 250000 | 0 | 0 | 0 | 0 | 250000 | 0 | 250000
|  |  | Lynn Hall Park Boardwalk & Dune Imp |  |  |  | A | [23 empty] | 70000 |  |  |  |  | 70000 | 0 | 70000
285 | D5 |  | Lakes Park Botanic Garden |  |  | Proposed | I-R | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 50000 | 0 | 0 | 0 | 0 | 50000 | 0 | 50000
287 | CW | NEW | Sports Complex Phase 1 New Fields |  |  | Proposed | T, G | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 5774000 | 0 | 0 | 0 | 0 | 5774000 | 0 | 5774000
288 |  |  | PARKS CAPITAL TOTAL |  |  |  |  | 2757978 | 898115 | 2572621 | 1258332 | 1288861 | 28402200 | 37359031 | 20473566 | 14614460 | 34006325 | 107409206 | 100000 | 13703301 | 13803301 | 0 | 0 | 0 | 0 | 0 | 13803301 | 0 | 0 |  | 7894000 | 150000 | 600000 | 0 | 0 | 8644000 | 3550000 | 133406507
289
290
291 |  |  | TOTAL CAPITAL BUDGET |  |  |  |  | 186750407 | 109914021 | 145048517 | 127365603 | 126827328 | 133570586 | 138664147 | 94721507 | 75020489.82 | 95069414 | 1185498977.82 | 83415603 | 247989943 | 323893006 | 0 | 0 | 0 | 0 | 0 | 310144691 | 0 | 0 |  | 125222445 | 62509546 | 111364754 | 256903986 | 146806868 | 702807599 | 592773273 | 2791224540.82
292 |  |  | Check for this year | [9 empty] | 161993753 | 149650131 | 96451470 | 74413188 |  |  |  |  | 83215524 | [5 empty] | 83215524 | 0 | 0
293 |  |  | Not in One World Adjustments | [10 empty] | 0 | 0 | [10 empty] | Not in One World | 0 | 0 | 0
294 |  |  | C/O's | [10 empty] | 0 | 0 |  |  |  |  | 241201769 | [5 empty] | c/o's | 0 | 0 | 0
295 |  |  | CIP Detail | [15 empty] | #REF! |  | 83215524 | [9 empty] | 125152445 | 62509546 | 111364754 | 256903986 | 146806868 | 702737599 | 592773273
296 |  |  | check line | [10 empty] | 149650131 | 96451470 |  |  |  | #REF! | -6788174 | 240677482 | [5 empty] | 226929167 | 0 | 0 |  | -70000 | 0 | 0 | 0 | 0 | -70000 | 0
[14 empty] | 10985984 | 1729963 | [5 empty] | 0 | [6 empty] | 0 | 0
Note on T1: bormanla: Add final expense line for 14/15 as t
Note on E7: bormanla: Name changed to add SII Source Identification & Impr
Note on E11: bormanla: Change name to add SII* Source Identification & Imp
Note on AC63: wolfek: $3,400,000 for a loan not in One World
Note on V121: bormanla: Per Dept sheet carryovers to high
Note on V123: bormanla: Check carryovers
Note on H240: bormanla: 15/16 cancelled project
Note on H241: bormanla: 15/16 cancelled project

## Second Review
REF # | MAP REF | FUNDING SOURCE | PROJ # | PROJECT NAME | PLAN | PLAN | All Prior Years | Expenses 5/6 | Expenses 6/7 | Expenses 7/8 | Expenses 8/9 | Expenses 9/10 | Expenses 10/11 | Expenses 11/12 | Expenses 12/13 | Expenses 13/14 | TOTAL PRIOR YEARS EXPENSES | BUDGET | PRELIMIN | BUDGET | $ | $ | CARRYOVER | $ | $ | CURRENT BUDGET FY 14/15 | AS OF | AS OF |  |  | BUDGET FY 15/16 | BUDGET FY 16/17 | BUDGET FY 17/18 | BUDGET FY 18/19 | BUDGET FY 19/20 | 5 YEAR BUDGET | 6-10 YEAR BUDGETS | TOTAL PROJECTED COST |  | DESCRIPTION | START UP |  | RECURRING
FUNDING SOURCE CODES: A = AD VALOREM; D = DEBT FINANCE; E = ENTERPRISE FUND; G = GRANT; GT = GAS TAX; I = IMPACT FEES; LA = LIBRARY AD VALOREM; S = SPECIAL; T = TDC; M = MSBU/TU
COMP PLAN CODES: R = REQUIRED; NR = NOT REQUIRED; F = FURTHERS SPECIFIC OR GENERALIZED REQUIREMENT OF LEE PLAN; CATEGORY CODE 1 THROUGH 5
1 |  |  |  | NATURAL RESOURCES
2 | CW | A-30155 | 208589 | Charlotte Harbor TMDL Compliance | 2 |  | 0 |  | 2190 | 12894 | 0 | 0 | 0 | 0 | 634 | 5456 | 21174 | 0 | 1493 | 1493 | [5 empty] | 1493 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1209916 | 1232583 |  | Prepare action plan & begin remedial projects in Matlacha Pass.
3 | CW | A-30100 | 208591 | Everglades-West Coast SII for TMDL Compl | 2 |  | 0 |  | 4380 | 25789 | 0 | 0 | 21920 | 105277 | 70796 | 30266 | 258428 | 0 | 585140 | 585140 | [5 empty] | 585140 | 0 | 0 |  |  | 200000 | 200000 | 200000 | 200000 | 200000 | 1000000 | 18000000 | 19843568 |  | *Source Identification and Improvements.
4 | B8 | A-30155 | 208548 | Fichter Creek Restoration | 5 |  | 0 |  | 38591 | 170556 | 176793 | 8740 | 2753 | 6290 | 0 | 0 | 403723 | 0 | 78088 | 78088 | [5 empty] | 78088 | 0 | 0 |  |  | 1400000 |  | 0 | 0 | 0 | 1400000 | 0 | 1881811 |  | Create a water conservation area through land acquisition in N Ft Myers/Alva.
5 |  | A-30100 | 208572 | Hendry Creek W Branch Water Quality Imp | [11 empty] | 0 | 0 | 400000 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 2500000 | 0 | 0 | 0 | 2500000 | 0 | 2500000 |  | Improvements to meet TMDL requirements in Hendry Creek watershed.
6 | A6 | A-30155 | 208567 | Nalle Grade Stormwater Park | 4 | [6 empty] | 0 | 0 | 403 | 34 | 101748 | 102185 | 0 | 797816 | 797816 | [5 empty] | 797816 | 0 | 0 |  |  | 0 | 3000000 | 0 | 0 | 0 | 3000000 | 0 | 3900001 |  | Provide hydrological restoration and flood relief in the Bayshore Creek watershed.
7 | C7 | A-30155 | 208557 | Sunniland/Nine Mile Run Drainage Improve | 3 | [9 empty] | 0 | 0 | 0 | 100000 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  |  | 0 | 350000 | 0 | 0 | 350000 | 0 | 350000 |  | Restore historical flows to Buckingham Trails Preserve.
8 | A5 | A-30100 | 208509 | Yellow Fever Creek Chain Improvements | 5 |  | 0 |  | 13035 | 95601 | 286 | 0 | 0 | 0 | 0 | 0 | 108922 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 571000 | 0 | 0 | 0 | 0 | 571000 | 0 | 679922 |  | Construct interconnect between Gator Slough Canal and Yellow Fever Creek in NFM and NE Cape Coral.
9 |  |  |  | NATURAL RESOURCES CAPITAL TOTAL |  |  | 0 | 0 | 58196 | 304840 | 177079 | 8740 | 24673 | 111970 | 71464 | 137470 | 894432 | 500000 | 1462537 | 1462537 | 0 | 0 | 0 | 0 | 0 | 1462537 | 0 | 0 |  |  | 2171000 | 5700000 | 550000 | 200000 | 200000 | 8821000 | 19209916 | 30387885
10 |  | A-30100 | 208573 | Natural Resources Master Project | [13 empty] | 1700000 |  | 1700000 | [5 empty] | 1700000 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
11
12 |  |  |  | SOLID WASTE
13 |  | E | NEW | LaBelle Transfer Station Expansion | [11 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 1000000 | 3500000 | 0 | 4500000 | 0 | 4500000 |  | Expand existing LeBelle Transfer Station
14 | D10 | E | 200936 | Landfill Gas Collection System | NR |  |  |  | 0 | 16906 | 0 | 0 | 0 | 0 | 0 | 0 | 16906 | 3250000 | 0 | 3250000 | [5 empty] | 3250000 | 0 | 0 |  |  | 0 | 0 | 250000 | 300000 | 0 | 550000 | 2000000 | 5816906
15 | C7 | E | 200929 | Recycling Facility |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 250000 | 0 | 0 | 0 | 0 | 250000 | 0 | 250000 |  | Preliminary study for expansion of Recycling Facility
16 | C7 | E | NEW | Household Chemical Waste Facility |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 500000 | 0 | 0 | 0 | 500000 | 0 | 500000 |  | Preliminary study for expansion of Household Chemical Facility
17 | C7 | E | 201007 | Waste to Energy |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 400000 | 0 | 0 | 0 | 0 | 400000 | 0 | 400000 |  | Preliminary study for expansion of WTE Facility
18 |  |  |  | SOLID WASTE CAPITAL TOTAL |  |  | 0 | 0 | 0 | 16906 | 0 | 0 | 0 | 0 | 0 | 0 | 16906 | 3250000 | 0 | 3250000 | 0 | 0 | 0 | 0 | 0 | 3250000 | 0 | 0 |  |  | 650000 | 500000 | 1250000 | 3800000 | 0 | 6200000 | 2000000 | 11466906
19
20 |  |  |  | GOVERNMENT FACILITIES
21 | CW | A, E, G48640 | 208894 | Park & Ride/Transit Stations | 3 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 136000 | 136000 | [5 empty] | 136000 | 0 | 0 |  |  | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | 3136000 |  | Park and Ride and Transfer Centers located east, west, north and south Lee County. | 16/17 | 160000
22 |  | S | 203416 | Tidemark Permitting Software Replace | [11 empty] | 0 | 0 | 1000000 | 0 | 1000000 | [5 empty] | 1000000 | 0 | 0 |  |  | 850000 | 0 | 0 | 0 | 0 | 850000 | 0 | 1850000 |  | Replace the permitting software. |  |  | 16/17 | 50000
23 | CW | A, G48640 | 208864 | Transit Passenger Amenities | 1 | [6 empty] | 0 | 0 | 270271 | 468549 | 507591 | 1246411 | 100000 | 771916 | 871916 | [5 empty] | 871916 | 0 | 0 |  |  | 500000 | 500000 | 500000 | 500000 | 500000 | 2500000 | 0 | 4618327 |  | Provide bus shelters, bike rakes, & ADA accessible improvements.
|  | I, 38200 | NEW | EMS Trail Dairy | [26 empty] | 500000 |  |  |  |  | 500000 | 0 | 500000
24 |  |  |  | GOVERNMENT FACILITIES CAPITAL TOTAL |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270271 | 468549 | 507591 | 1246411 | 1100000 | 907916 | 2007916 | 0 | 0 | 0 | 0 | 0 | 2007916 | 0 | 0 | 0 |  | 4850000 | 500000 | 500000 | 500000 | 500000 | 6850000 | 0 | 10104327
25
26 |  |  |  | LIBRARY PROJECTS
27 |  | LA | 203627 | Two Community Libraries | [11 empty] | 0 | 0 | 2000000 | 0 | 2000000 | [5 empty] | 2000000 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
28 |  | LA | 201005 | North Ft Myers Library | [14 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 5986562.5 | 5986562.5 | 0 | 0 | 0 | 11973125 | 0 | 11973125 |  | Construct a 25,000 square ft community library | 16/17 | 600000 | 16/17 | 300000
29 |  | LA | 201006 | Bonita Springs Library | [14 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 5347812.5 | 5347812.5 | 0 | 0 | 0 | 10695625 | 0 | 10695625 |  | Construct a 25,000 square ft community library | 16/17 | 600000 | 17/18 | 310000
30 |  |  |  | LIBRARY CAPITAL TOTAL |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 |  |  | 11334375 | 11334375 | 0 | 0 | 0 | 22668750 | 0 | 24668750
31
32 |  |  |  | TRANSPORTATION DEPARTMENT
33 | B7,8 | GT,i25,A | 205075 | Alico Rd 4L - Ben Hill/Airport Rd | 5 | [6 empty] | 0 | 34703 | 663598 | 0 | 214281 | 912582 | 0 | 1672579 | 1672579 | [5 empty] | 1672579 | 0 | 0 |  |  | 0 | 0 | 11500000 | 540000 | 0 | 12040000 | 0 | 14625161 |  | Widen 2 lane rural arterial to 4 lanes. 1.78 miles |  |  | 15/16 | 45656
34 |  | I25 | NEW | Alico Rd Connection | [12 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2240868 | 2240868 | 64000000 |  |  | Two lane arterial extension to future 4-lane road, linking Airport, FGCU more directly to Lehigh.
35 | CW | GT,I21-25 | 206002 | Bicycle/Pedestrian Facilities | 4 | 40.4.2 | 12382165 | 1151927 | 3009199 | 1692691 | 2422346 | 382378 | 31250 | 135022 | 225361 | 191171 | 18607940 | 770000 | 640905 | 1410905 | [5 empty] | 1410905 | 0 | 0 |  |  | 394000 | 2437000 | 1312000 | 843000 | 1161000 | 6147000 | 3700000 | 29865845 |  | Design & construct bike paths, lanes and sidewalks |  |  | 15/16 | 74949
36 | F6 | GT, E30720 | 205724 | Big Carlos Pass Bridge Replacement | 1 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 3500000 | 1500000 | 5000000 | [5 empty] | 5000000 | 0 | 0 |  |  | 3500000 | 3500000 | 3500000 | 3500000 | 1000000 | 15000000 | 25300000 | 45300000 |  | Replace 2 lane bascule bridge with 2 lane fixed span bridge
37 |  | GT | NEW | Big Hickory Pass Bridge Replacement | [12 empty] | 0 |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 10043000 | 10043000 |  | Replacement of existing 2-lane span bridge
38 | G7 | I-24,A,S | 205723 | Bonita Beach Road - Phase III | 5 |  |  |  | 0 | 462543 | 795030 | 234741 | 282487 | 209463 | 1080 | 0 | 1994332 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 23700000 | 25694332 |  | Widen road from 4 to 6 lanes from west of US 41 to Old 41 2.0 miles
39 | B,C4 | E30721, A, I-22, S | 204088 | Burnt Store Road Four Laning-78 to Van Buren | 5 |  | 387571 | 2175358 | 1177479 | 1583139 | 573961 | 1543038 | 592703 | 212946 | 500290 | 882743 | 9571084 | 13325000 | 1364311 | 14689311 | [5 empty] | 14689311 | 0 | 0 |  |  | 6580000 | 5042246 | 897754 | 8700000 | 630000 | 21850000 | 0 | 46110395 |  | Widen 2 lane rural arterial to 4 lanes divided road from Pine Island to Van Buren 4.86 miles |  |  | 15/16 | 8400
40 |  | E30721, | NEW | Cape Coral Bridge WB Span Replacement | [11 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1000000 | 4000000 | 5000000 | 82500000 | 87500000 |  | Replace the westbound span fo cc bridge
41 |  | I23 | NEW | Colonial Blvd Alternatives Analysis | [15 empty] | 0 | [5 empty] | 0 |  |  | 0 |  | 0 | 0 | 0 | 350000 | 0 | 350000 | 0 | 350000 |  | Evaluate Imp options on Colonial Blvd between McGregor and US 41
42 | B5 | GT | 205082 | Corbett Rd Widening/Resurfacing | 3 | [9 empty] | 0 | 0 | 0 | 150000 | 0 | 150000 | [5 empty] | 150000 | 0 | 0 |  |  | 690000 | 0 | 0 | 0 | 0 | 690000 | 0 | 840000 |  | Widen existing pavement to allow for 11 foot travel lanes, app bike path
43 | D6 | I23 |  | Crystal Drive 2 Lane Divided | 5 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 850000 | 850000 | 1700000 | 5750000 | 7450000 |  | Reconstruct 2 lane undivided roadway to 2 lane dividied secton with bike lanes and sidewalks
44 | D6 | A | 205077 | Crystal/Plantation Roundabout | 4 | [8 empty] | 0 | 0 | 16687 | 1125 | 0 | 560339 | 560339 | [5 empty] | 560339 | 0 | 0 |  |  | 25000 | 0 | 0 | 0 | 0 | 25000 | 0 | 586464 |  | Construct roundabout
45 | E5 | GT,I-24,A | 205067 | Estero Blvd Improvements | 3 |  |  |  | 0 | 573729 | 564674 | 305276 | 59303 | 97072 | 495621 | 516584 | 2612259 | 750000 | 8419621 | 9169621 | [5 empty] | 9169621 | 0 | 0 |  |  | 7000000 | 750000 | 7300000 | 750000 | 7000000 | 22800000 | 15500000 | 50081880 |  | Imp 2 lane roadway in Town of FM Bch from Matanzas Pass to Bgd Carlos Pass |  |  | 15/16 | 39600
46 |  | GT | 209246 | Gunnery Rd/8th St Intersection Imp | [13 empty] | 0 | 0 | 0 | [5 empty] | 0 |  |  |  |  | 60000 | 850000 | 0 | 0 | 0 | 910000 | 0 | 910000 |  | Signalize the intersection and turn lane improvements
47 | C8 | I-23,A,GT | 205063 | Homestead 4L / Sunrise-Alabama | 5 |  | 0 |  | 621983 | 1138204 | 342534 | 113098 | 28928 | 20294 | 65983 | 47583 | 2362189 | 1750000 | 2730668 | 4480668 | [5 empty] | 4480668 | 0 | 0 |  |  | 13500000 | 690000 | 0 | 0 | 0 | 14190000 | 0 | 21032857 |  | Widen existing 2 lane to 4 lanes from Sunrise Blvd to Alabama Rd |  |  | 16/17 | 95020
48 | B5 | I-22 | 209247 | Kismet/Littleton Realignment | 5 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 137500 | 675000 | 825000 | 0 | 1637500 | 0 | 1637500 |  | Realignment of eastern end of Kismet to connect with Littleton
49 |  | GT | NEW | Lee Blvd/Gunnery Rd Intersection Imp | [15 empty] | 0 | [5 empty] | 0 | 0 | 0 |  |  | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | 500000 |  | Improve congestion at intersection
50 |  | GT, A,E30720 | NEW | Little Carlos Pass Bridge Replacement | [15 empty] | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3270000 | 3270000 |  | Replacement of existing 2-lane span bridge
51 |  | GT | NEW | Little Pine Island Pass Bridge Replacment | [15 empty] | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3385000 | 3385000 |  | Replacement of existing 2-lane span bridge
52 | B7 | I-23,A | 205068 | Luckett Road 4L / Ortiz to I-75 | 5 |  | 0 |  | 0 | 538832 | 151 | 0 | 0 | 11810 | 0 | 0 | 550793 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3519000 | 4069793 |  | Widen 2 lane road to 4 lanes .46 miles
53 |  | E, GT | NEW | New Pass Bridge Replacement | [22 empty] | 0 | 0 |  |  | 0 | 0 | 2700000 | 5000000 | 5000000 | 12700000 | 7060000 | 19760000 |  | Replacement of existing 2-lane span bridge
54 | C6 | A, I-23 | 204100 | North Airport Road Extension West | 4 |  |  |  | 0 | 0 | 0 | 1350 | 235718.25 | 100358.15 | 92114.36 | 18283.5 | 447824.26 | 4195000 | 277177 | 4472177 | [5 empty] | 4472177 | 0 | 0 |  |  | 70000 | 0 | 0 | 0 | 0 | 70000 | 0 | 4990001.26 |  | Extend existing 2 lane east to Metro |  |  | 15/16 | 14524
55 | C7 | I-23,A |  | Ortiz 4L / Colonial-MLK | 5 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 1550000 | 0 | 0 | 1550000 | 13269000 | 14819000 |  | Widen 2 lane to 4 lane 1.73 miles
56 | C7 | I-23,A | 205056 | Ortiz Avenue/SR80 - Luckett | 5 |  | 0 | 368814 | 2660268 | 2282520 | 1829137 | 643708 | 620568 | 1269 | 7432 | 920 | 8414636 | 0 | 3143703 | 3143703 | [5 empty] | 3143703 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 12450000 | 24008339 |  | Widen 2 lane to 4 lane 1.33 miles
57 | C7 | I-23,A | 204072 | Ortiz Four Laning - MLK to Luckett | 5 | 37.1 POL 36.1.5 | 78974 | 1301297 | 3377302 | 2110669 | 1516558 | 240660 | 115320 | 352093 | 65158 | 42840 | 9200871 | 0 | 604811 | 604811 | [5 empty] | 604811 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 9325000 | 19130682 |  | Widen 2 lane to 4 lane 1.25 miles
58 |  | S, GT | 205081 | Palomino Lane Improvements | [11 empty] | 0 | 0 | 0 | 132614 | 132614 | [5 empty] | 169636 | 0 | 0 |  |  | 80364 | 1700000 | 0 | 0 | 0 | 1780364 | 0 | 1950000 |  | Improvement to existing 2 lane collector road, bike path.
59 | CW | GT | 206759 | Signal System ATMS Upgrades | 3 | [6 empty] | 0 | 0 | 623277 | 800312.82 | 644528 | 2068117.82 | 750000 | 205925 | 955925 | [5 empty] | 955925 | 0 | 0 |  |  | 750000 | 750000 | 750000 | 750000 | 750000 | 3750000 | 0 | 6774042.82 |  | Upgrade existing traffic signal system |  |  | 15/16 | 9500
60 |  | GT | NEW | Sunshine Blvd/8th St SW Roundabout | [13 empty] | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 200000 | 200000 | 550000 | 950000 | 0 | 950000 |  | Construct roundabout
61 | D7 | I-24,A,GT | 204053 | Three Oaks Pkwy Extension, North | R | 36.1.1;36.1.4 | 1990373 | 79909 | 208499 | 3482379 | 608014 | 50814 | 361087 | 149075 | 6488 | 0 | 6936638 | 0 | 5690477 | 5690477 | [5 empty] | 5690477 | 0 | 0 |  |  | 0 | 0 | 3000000 | 0 | 3000000 | 6000000 | 37250000 | 55877115 |  | 4 lane arterial extension from north of Alico to Daniels 3.5 miles
62 | C5,E4 | E | 205818 | Toll Interoperability | 3 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 150000 | 150000 | [5 empty] | 150000 | 0 | 0 |  |  | 150000 | 150000 | 150000 | 150000 | 150000 | 750000 | 0 | 900000 |  | Upgrade software & hardware
63 | C5,E4 | E |  | Toll System Replacement | NR |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 2250000 | 2250000 | 0 | 0 | 4500000 | 0 | 4500000 |  | Replace Leeway Service Center ARCS system.
64 |  |  |  | TRANSPORTATION CAPITAL TOTAL |  |  | 14839083 | 5077305 | 11054730 | 13864706 | 8652405 | 3515063 | 2362067.25 | 2576277.15 | 2259840.18 | 2575620.5 | 63680391.08 | 25190000 | 27093130 | 52283130 | 0 | 0 | 0 | 0 | 0 | 52320152 | 0 | 0 |  |  | 33299364 | 18256746 | 35784754 | 23458000 | 26331868 | 137130732 | 320021000 | 506911407.08
65
66 |  |  |  | UTILITIES
67 | E7 | E | 207614 | Alico Rd 4L-Ben Hill/Airport Haul-WM Reloc | 3 | [8 empty] | 0 | 0 | 3497 | 3497 | 0 | 196320 | 196320 | [5 empty] | 196320 | 0 | 0 |  |  | 0 | 0 | 3750000 | 0 | 0 | 3750000 | 0 | 3949817 |  | Relocate existing water main.
68 | C6 | E |  | Bayshore Rd 24" WM-Samville to N. Tamiami | 5 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3450000 | 3450000 |  | Install 13,400 LF of 24 " water main from Samville Rd to N Tamiami Trail.
69 | E7 | E | 207334 | Ben Hill Griffin Force Main Improve South | 5 | [9 empty] | 0 | 0 | 0 | 425000 | -425000 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 450000 | 250000 | 4950000 | 0 | 0 | 5650000 | 0 | 5650000 |  | Force main improvements along Ben Hill Griffin Parkway S of FGCU Parkway to the Pinewoods WTP.
70 | C7 | E |  | Colonial 30" Water Main-Ortiz to Gumnnery | 5 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 8400000 | 8400000 |  | Install 33,000 LF of 24" water main from Ortiz to Gunnery Rd.
71 |  | E |  | Corkscrew Groundwater ASR System | [11 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 21970000 | 21970000 |  | Additional raw water spply source for utilization by Corkscrew & Geen Meadows WTP
72 |  | E |  | Corkscrew Production Well Panal Rep | [11 empty] | 0 | 0 | 1170240 | 0 | 1170240 | [5 empty] | 1170240 | 0 | 0 |  |  | 1250000 | 0 | 0 | 0 | 0 | 1250000 | 0 | 2420240 |  | Replace production well panel to control flow rates.
73 | CW | E | 207448 | County-Wide Fiber Network | 1 | [8 empty] | 0 | 88510 | 172788 | 261298 | 100000 | 88702 | 188702 | [5 empty] | 188702 | 0 | 0 |  |  | 100000 | 50000 | 50000 | 25000 | 25000 | 250000 | 100000 | 800000 |  | Install network for LCU facilities across the county.
74 |  | E | 207307 | Daniels Pkwy Forcemain Ext to Gateway | [31 empty] | 0 | 2250000 |  |  | Construct a new Force Main along Daniels Parkway.
75 | E5 | E |  | Deep Injection Well - #2 | 5 | OBJ 54.1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 400000 | 0 | 6000000 | 6400000 | 0 | 6400000 |  | Install a deep injection well at FMBWWTP as required by FDEP.
76 | A5 | E | 207606 | Del Prado Water Main Replacement | 3 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 200000 | 1075000 | 0 | 0 | 0 | 1275000 | 0 | 1275000 |  | Replace existing 16" PVC water main.
77 | CW | E | 207416 | DOT Project Utility Relocations | 3 |  | 509542 | 354823 | 13105 | 368506 | 340282 | 334484 | 213047 | 326053 | 54111 | 6230 | 2520183 | 0 | 147078 | 147078 | [5 empty] | 147078 | 0 | 0 |  |  | 100000 | 0 | 0 | 0 | 0 | 100000 | 0 | 2767261 |  | Misc FDO & LCDOT relocating of lines for roadway pjts
78 | CW | E | 207429 | Electrical Equipment Upgrades & Replacements | 3 |  | 314042 | 174091 | 168057 | 132422 | 567577 | 180315 | 640281 | 575575 | 108256 | 208452 | 3069068 | 536100 | 202619 | 738719 | [5 empty] | 738719 | 0 | 0 |  |  | 510400 | 233800 | 120000 | 70000 | 70000 | 1004200 | 3300000 | 8111987 |  | Replace old electrical equipment and upgrade equipment to meet new load demands.
79 | CW | E | 207446 | Energy Management Initiatives Program | NR | [6 empty] | 0 | 54065 | 135695 | 34134 | 85181 | 309075 | 100079 | 32869 | 132948 | [5 empty] | 132948 | 0 | 0 |  |  | 100000 | 100000 | 100000 | 25000 | 25000 | 350000 | 100000 | 892023 |  | Purchase power monitoring equipment.
80 | E5, F5 | E | 207326 | Estero Blvd Force Main Relocation | 3 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 19595 | 19595 | 150000 | 1011394 | 1161394 | [5 empty] | 1161394 | 0 | 0 |  |  | 1450000 | 150000 | 1450000 | 150000 | 1450000 | 4650000 | 1725000 | 7555989 |  | Relocate force main to allow for construction of roadway improvements.
81 | CW | E | 207447 | Facility Wide Security System | 2 | [7 empty] | 0 | 3292 | 18051 | 23089 | 44432 | 25000 | 48155 | 73155 | [5 empty] | 73155 | 0 | 0 |  |  | 75000 | 75000 | 25000 | 25000 | 25000 | 225000 | 175000 | 517587 |  | Install cameras, gates, entrance systems at all facilities.
82 | CW | E | 207613 | Fiber Optic Upgrades | 3 | [5 empty] | 0 | 0 | 0 | 76601 | 206033 | 105690 | 388324 | 0 | 626341 | 626341 | [5 empty] | 626341 | 0 | 0 |  |  | 2900000 | 0 | 0 | 0 | 0 | 2900000 | 0 | 3914665 |  | Install fiber optics to each well and tie into the plant PLC.
83 | D5 | E | 207293 | Fiesta Village Sewer Collection System Improve | 5 |  | 0 | 108 | 5826 | 31578 | 0 | 0 | 0 | 0 | 0 | 0 | 37512 | 650000 | -650000 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 150000 | 950000 | 0 | 0 | 0 | 1100000 | 0 | 1137512 |  | Replace ctrl system
84 |  | E |  | Fiesta Village WWTP Control Sys Upgrade |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | 0 | 0 |  |  | 100000 | 850000 | 0 | 0 | 0 | 950000 | 0 | 950000 |  | Construct a new master lift station.
85 | D5 | E |  | Fiesta Village WWTP RM Upgrade | 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 300000 | 100000 | 4325000 | 0 | 4725000 | 0 | 4725000 |  | Site selection, engineering design, permitting, bidding and construction of one Class I underground injection ctol deep injection well
86 |  | E |  | Fiesta Village WWTP Deep Injection Well |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 462500 | 6900000 | 0 | 0 | 0 | 7362500 | 0 | 7362500 |  | Upgrade the reuse system to increase reuse flow capacity.
87 | D5 | E | 207450 | Fiesta WWTP Sludge Handling | 1 |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 850000 | -850000 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 150000 | 950000 | 0 | 0 | 0 | 1100000 | 0 | 1100000 |  | Design and construct permanent dewatering equipment.
88 |  | E | NEW | FMB Main Switchgear Replacement | [11 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 232000 | 1542000 | 0 | 0 | 1774000 | 0 | 1774000 |  | Replace the existing pre-stressed Equalization tank, pumps and dome.
89 | E5 | E | 207451 | FMB WWTP Controls System Replacement | 3 | [9 empty] | 0 | 0 | 0 | 0 | 600000 | 600000 | [5 empty] | 600000 | 0 | 0 |  |  | 700000 | 0 | 0 | 0 | 0 | 700000 | 0 | 1300000 |  | Replace main switchgear
90 | E5 | E |  | FMB WWTP EQ Tank Replacement | 3 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 480000 | 8200000 | 0 | 8680000 | 0 | 8680000 |  | Replace obsolete ctrl system of WWTP with new PLC system
91 |  | E |  | Gateway WWTP Sludge Dewatering System Roof | [22 empty] | 0 | 0 |  |  | 0 | 65000 | 0 | 0 | 0 | 65000 | 0 | 65000 |  | Provide covered building for storage and operation of centrifuge.
92 | CW | E | 207247 | Inflow & Infiltration Improvement | 3 |  | 1175459 | 179309 | 238543 | 670947 | 704876 | 1569487 | 1342580 | 427224 | 1354610 | 455689 | 8118724 | 500000 | 239892 | 739892 | [5 empty] | 739892 | 0 | 0 |  |  | 500000 | 500000 | 500000 | 500000 | 500000 | 2500000 | 2000000 | 13358616 |  | Rehab gravity lines & pump stations which cause inflow and infiltration.
93 | CW | E | 207430 | Instrumentation Upgrades & Improvements | 3 |  | 666455 | 184929 | 86731 | 10467 | 183361 | 152678 | 129714 | 78521 | 0 | 92594 | 1585450 | 115100 | 6110 | 121210 | [5 empty] | 121210 | 0 | 0 |  |  | 202500 | 150000 | 150000 | 100000 | 100000 | 702500 | 600000 | 3009160 |  | Install new equip as needed to improve control & meet standards and specifications.
94 | E7 | E |  | Interconnect Pinewoods Distribution Sys | 3 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 4850000 | 4850000 |  | Install 19,000 LF of watermain from Corkscrew Rd to Airport Haul Reservoir.
95 | CW | E | 207444 | LCU Generator Replace & Improve | 3 |  |  |  |  | 0 | 0 | 14405 | 67963 | 638269 | 100335 | 391268 | 1212240 | 340000 | 19185 | 359185 | [5 empty] | 359185 | 0 | 0 |  |  | 348000 | 198000 | 0 | 0 | 0 | 546000 | 1000000 | 3117425 |  | Purchase new generators as needed.
96 |  | E |  | Mariana Ave WM Replacement | [12 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 60000 | 500000 | 0 | 0 | 0 | 560000 | 0 | 560000 |  | Replace appr 5000LF of existing 2" & 6" water main along Mariana Ave
97 |  | E | 207335 | Master Lift Station 7716 Improvements | [11 empty] | 0 | 0 | 800000 | -800000 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 825000 | 1425000 | 0 | 0 | 0 | 2250000 | 0 | 2250000 |  | Replace with a new station at a new location.
98 |  | R |  | McGregor-Tanglewood Force Main Rep | [12 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 440000 | 2900000 | 0 | 0 | 3340000 | 0 | 3340000 |  | Replace24" DIP force main along McGregor from N Whiskey Ck Bridege to Tanglewood
99 | D5 | E | 207453 | McGregor Blvd Water Main Replacement | 3 | [8 empty] | 0 | 0 | 0 | 0 | 2000000 | 900000 | 2900000 | [5 empty] | 2900000 | 0 | 0 |  |  | 4000000 | 0 | 0 | 0 | 0 | 4000000 | 0 | 6900000 |  | Replace existing water main with a new 12" water main. From College Parkway to Whiskey Creek Bridge.
100 | B7 | E | 207618 | NLC WTP Deep Injection Well Backup | 3 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 425000 | 5350000 | 0 | 0 | 5775000 | 0 | 5775000 |  | Install a backup Deep Injection Well.
101 | A7 | E |  | North Lee County WTP Expansion to 15 MGD | 5 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2300000 | 0 | 2300000 | 28300000 | 30600000 |  | Expand the existing NLC WTP from 10 to 15 MGD.
102 | A7 | E | 207619 | NLC WTP Wellfield Expansion to 15 MGD | 5 | [9 empty] | 0 | 1013 | 1013 | 0 | 250000 | 250000 | [5 empty] | 250000 | 0 | 0 |  |  | 0 | 0 | 0 | 2618986 | 0 | 2618986 | 10580000 | 13449999 |  | Construct 6 additional lower Hawthorn production wells.
103 | C7,D7 | E |  | North-South 30" Water Main-SR80 to AHR | 3,5 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 28200000 | 28200000 |  | Install 74,000 LF of 30" water main along Buckingham Rd from SR 82 to end at the Airport Haul Reservoir.
104 | B5.B6 | E |  | N Tamiami 24" WM-Pondella to Cleveland | 5 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 5600000 | 5600000 |  | Install 22,000 LF of 24" water main along N Tamiami Trail from Pondella Rd to Cleveland Avenue.
105 |  | E |  | Olga WTP MCC Replacement | [11 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 500000 | 500000 | 0 | 0 | 0 | 1000000 | 0 | 1000000 |  | Replace motor control one & motor control two over a 2 year period.
106 | B6 | E | 207454 | Operations Building Replacement | 3 | [9 empty] | 0 | 0 | 0 | 150000 | -150000 | 0 | [5 empty] | 0 | 0 | 0 | 75000 |  | 75000 | 0 | 0 | 0 | 0 | 75000 | 2500000 | 2575000 |  | Construct a new building for Utilities Operations.
107 | B5 | E |  | Orange Grove WM-Pondella to Hancock | 3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 100000 | 700000 | 0 | 0 | 800000 | 0 | 800000 |  | Construct a 12" water main along Orange Grove Blvd. to Hancock Bridge Parkway.
108 | B7 | E |  | Ortiz FM - Palm Beach to Ballard | 3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2150000 | 2150000 |  | Replace the aging and failing sewer force main along Ortiz Avenue.
109 | B7 | E |  | Ortiz Ave Utility Relocation-MLK to SR80 | 3 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 6000000 | 6000000 |  | Relocate existing utilities in conflict with the proposed roadway.
110 | D6 | E | 207127 | Page Park Waterline Improvements | 3 |  | 0 |  | 0 | 9287 | 0 | 0 | 0 | 0 | 58487 | 154209 | 221983 | 1300000 | 443784 | 1743784 | [5 empty] | 1743784 | 0 | 0 |  |  | 4100000 | 0 | 0 | 0 | 0 | 4100000 | 0 | 6065767 |  | Replace old cast iron & small pipes in the Page Park area.
111 | D3 | E | 207238 | Pine Island Sewer Transmission System | 5 |  | 27767 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 27767 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4027767 |  | Install a main from Pine Island Road to Bookelia and construct a master lift station.
112 | D3 | E | 207239 | Pine Island WWTP Expansion | 5 |  | 403481 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 403481 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 6500000 | 6903481 |  | Expand Pine Island Wastewater Treatment Plant to 1 MGD.
113 |  | E | NEW | Pine Ridge FM-FMB WWTP/Gulf Reflections | [11 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 230000 | 200000 | 1533000 | 0 | 0 | 1963000 | 0 | 1963000 |  | Replace 4,000 ft of force main along Pine Ridge Rd from FMB WWTP to Gulf Reflection Drive.
114 | F7 | E |  | Pinewoods Odor Control Scrubber | 3 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 200000 | 0 | 0 | 0 | 200000 | 0 | 200000 |  | Install a redundant odor control scrubber system.
115 | F7 | E |  | Pinewoods WTP Degasifiers Replacement | 3 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 759000 | 0 | 0 | 0 | 759000 | 0 | 759000 |  | Replace 3 leaking degasifier units.
116 | D5 | E | 207284 | Reclaim Water ASR | 5 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 1260000 | 0 | 4500000 | 0 | 0 | 5760000 | 0 | 5760000 |  | Construction of a reclaimed water ASR.
117 | CW | E | 207455 | Reuse System & Site Improvements | 3 | [9 empty] | 0 | 57160 | 57160 | 0 | 447645 | 447645 | [5 empty] | 447645 | 0 | 0 |  |  | 0 | 1500000 | 1500000 | 0 | 0 | 3000000 | 0 | 3504805 |  | Install equipment replacements and upgrades.
118 | E7 | E | 207162 | San Carlos Blvd Improv-Linda Loma to Kelly | 3 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1800000 | 1800000 |  | Replace 14" water main with a 16" water main, from just north of Summerlin Road to Kelly Road.
119 | CW | E | 207424 | SCADA Upgrades & Improvements | 3 |  | 586870 | 223717 | 170815 | 222618 | 307965 | 7668 | 164024 | 181483 | 249714 | 556144 | 2671018 | 700000 | 405674 | 1105674 | [5 empty] | 1105674 | 0 | 0 |  |  | 400000 | 400000 | 300000 | 200000 | 200000 | 1500000 | 1500000 | 6776692 |  | Install new & upgrade SCADA equipment though out the system.
120 | CW | E | 207456 | Secondary Containments-Chemical Tanks | 3 | [9 empty] | 0 | 38048 | 38048 | 0 | 144313 | 144313 | [5 empty] | 144313 | 0 | 0 |  |  | 150000 | 150000 | 150000 | 400000 | 0 | 850000 | 0 | 1032361 |  | Adding Secondary containment areas to each of chemical tanks at WWTP
121 | CW | E | 207184 | SFM Water Transmission Line Improvements | 5 |  | 0 |  | 0 | 132553 | 110241 | 16077 | 29635 | 41454 | 0 | 0 | 329960 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 200000 | 2000000 | 2200000 | 0 | 2529960 |  | Install 16" water main along Crystal Drive and 12" water main along Winkler Road.
122 | C6 | E | 207194 | Summerlin Road Water System Improvements | 5 |  | 0 |  | 0 | 34752 | 343135 | 99179 | 29275 | 13181 | 0 | 0 | 519522 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 6379248 | 6898770 |  | Install water main in the Summerlin & Winkler area.
123 | E7 | E | 207325 | Three Oaks Oxidation Ditch Improvements | 4 | [7 empty] | 0 | 0 | 77422 | 564631 | 642053 | 17000000 | 1330002 | 18330002 | [5 empty] | 18093947 | 0 | 0 |  |  | 10864855 | 0 | 0 | 0 | 0 | 10864855 | 0 | 29600855 |  | Provides additional air to the oxidation ditches.
124 | E7 | E |  | Three Oaks WWTP Expansion to 8 MGD | 5 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 28000000 | 28000000 |  | Expand the plant to 8 MGD.
125 | B7 | E | 207164 | Tice Street Loop | 3 |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 56225 | 31249 | 87474 | 0 | 13065 | 13065 | [5 empty] | 13065 | 0 | 0 |  |  | 900000 | 0 | 0 | 0 | 0 | 900000 | 0 | 1000539 |  | Install water lines in the Tice area to complete the connection of the water distribution system.
126 | D7 | E |  | Treeline WM-Terminal Access to Daniels | 5 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 4430000 | 4430000 |  | Construct a 30" water transmission line along Treeline.
127 | B5 | E | 207170 | US 41 Watermain Improvement | 3 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 217967 | 1397271 | 293295 | 1908533 | 3800000 |  | 3800000 | [5 empty] | 3800000 | 0 | 0 |  |  | 2500000 | 0 | 0 | 0 | 0 | 2500000 | 0 | 8208533 |  | Replace 10" water main along US 41 from Alico Road to Cypress Lake Dr.
128 | CW | E | 207229 | Wastewater System Improvements | 3 |  | 479528 | 468821 | 196524 | 85350 | 172861 | 242399 | 237657 | 225803 | 229409 | 335737 | 2674089 | 250000 | 1327 | 251327 | [5 empty] | 251327 | 0 | 0 |  |  | 250000 | 250000 | 250000 | 250000 | 250000 | 1250000 | 1000000 | 5175416 |  | County-wide equipment replacement within wastewater system.
129 | CW | E | 207138 | Wastewater Treatment Plant Improvements | 1 |  | 1125126 | 171618 | 213466 | 488549 | 221710 | 35460 | 943665 | 115298 | 93393 | 566110 | 3974395 | 380000 | 533776 | 913776 | [5 empty] | 913776 | 0 | 0 |  |  | 370000 | 245000 | 500000 | 0 | 0 | 1115000 | 2900000 | 8903171 |  | County-wide replacement/improvements to the wastewater plants.
130 | CW | E | 207094 | Water System Improvements | 3 |  | 523350 | 127468 | 10190 | 56792 | 283756 | 951690 | 483900 | 457779 | 575264 | 509225 | 3979414 | 250000 | 283522 | 533522 | [5 empty] | 533522 | 0 | 0 |  |  | 500000 | 500000 | 500000 | 500000 | 500000 | 2500000 | 1000000 | 8012936 |  | County-wide equipment improvements within the water system.
131 | D7 | E | 207193 | Water Transmission Ben Hill To Treeline | 5 |  | 0 | 39031 | 2491114 | 249191 | 288202 | 19465 | 82460 | 7936 | 45477 | 131874 | 3354750 | 0 | 179607 | 179607 | [5 empty] | 179607 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 6960000 | 10494357 |  | Install water transmission lines from Fiddlesticks to Old Gladiolus.
132 | CW | E | 207268 | Water Treatment Plant Improvements | 1 |  | 837185 | 429675 | 287247 | 248580 | 78439 | 1159839 | 1551050 | 661203 | 163138 | 394560 | 5810916 | 180600 | 306069 | 486669 | [5 empty] | 486669 | 0 | 0 |  |  | 90000 | 0 | 0 | 0 | 0 | 90000 | 0 | 6387585 |  | County-wide replacement/improvements to the water plants.
133 | E7 | E | 207426 | Water/Sewer Line Relocation-Three Oaks Ext. | 3 |  | 250 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 300500 |  | Relocate water and sewer lines along Fiddlesticks Blvd.
134 | CW | E | 207149 | Well Redevelopment/Upgrade & Rebuild | 3,5 |  | 678714 | 79716 | 232330 | 597002 | 760980 | 611615 | 562164 | 256663 | 302838 | 385 | 4082407 | 130000 | 404081 | 534081 | [5 empty] | 534081 | 0 | 0 |  |  | 130000 | 130000 | 130000 | 130000 | 130000 | 650000 | 710000 | 5976488 |  | Upgrade, reconstruct & replace old wells through out the system.
135 |  | E | NEW | Winkler Road Watermain Improvement | [11 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 200000 | 2100000 | 0 | 0 | 0 | 2300000 | 0 | 2300000 |  | Install 12" water main from Cypress Lake Dr to McGregor Blvd.
136 | C5 | E | 207183 | Waterway Estates Water Transmission Line Imp | 5 |  | 0 |  | 72350 | 119076 | 11669 | 12050 | 28144 | 10835 | 0 | 0 | 254124 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 150000 | 1100000 | 0 | 0 | 1250000 | 0 | 1504124 |  | Construction of a 12" Water Main on Pondella Rd
137 | C6 | E | 207620 | Work Dr Industrial Pk WM Improvements | 3,4 | [9 empty] | 0 | 0 | 0 | 2075000 | 0 | 2075000 | [5 empty] | 2075000 | 0 | 0 |  |  | 600000 | 2000000 | 0 | 0 | 0 | 2600000 | 0 | 4675000 |  | Upgrade existing water main along Cargo St and Katanga Ct in our service area of the City of Ft Myers.
138 |  |  |  | UTILITIES CAPITAL TOTAL |  |  | 7327769 | 2433556 | 4186298 | 3457670 | 4375054 | 5406811 | 6559624 | 4450832 | 5212678 | 5197713 | 48608005 | 33977119 | 5986530 | 39963649 | 0 | 0 | 0 | 0 | 0 | 39727594 | 0 | 0 |  |  | 37753255 | 25002800 | 33030000 | 20018986 | 11275000 | 127080041 | 198729248 | 411894888
139
140 |  |  |  | PARKS - COMMUNITY & REGIONAL
141 | C6 | I-24 | 202146 | Brooks Park Master Plan & Improvements | 5 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | -95 | 0 | -95 | 0 | 53856 | 53856 | [5 empty] | 53856 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1250000 | 1303761 |  | Prepare a master plan for Brooks Park & construct a parking lot, clubhouse and restrooms.
142 | A8 | I-R | 202153 | Caloosahatchee Reg Pk Maint Building | 3 | [9 empty] | 0 | 3400 | 3400 | 0 | 96600 | 96600 | [5 empty] | 96600 | 0 | 0 |  |  | 250000 | 0 | 0 | 0 | 0 | 250000 | 0 | 350000 |  | Construct a maint at Caloosahatchee Reg Park.
143 | CW | I-R | 202154 | Greenways | 5 | [8 empty] | 0 | 0 | 0 | 0 | 100000 | 0 | 100000 | [5 empty] | 100000 | 0 | 0 |  |  | 0 | 150000 | 600000 | 0 | 0 | 750000 | 1150000 | 2000000 |  | Construct Greenways and Blueways. Project - Able Canal in Lehigh
144 | B8 | I - R |  | Idalia Park | 5 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 |  | Development of a passive park on the Caloosahatchee River.
145 |  | I-23 | 201865 | Lehigh Park Acquisition & Improvements | 3 | [6 empty] | 0 | 98012 | 442874 | 2501796 | 246726 | 3289408 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | 4789408 |  | Continuation of park improvements in Lehigh. 30-acres along Joal Blvd.
146 | B2 | A |  | Pine Island Comm Marina Mstr Plan & Impr | 3 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1050000 | 1050000 |  | Improvements to the property at the marina.
147 | D5 | A |  | Terry Park Main/Storage Bldg |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 250000 | 0 | 0 | 0 | 0 | 250000 | 0 | 250000 |  | Replace storage building for equipment.
148 | D5 | I-R | 209265 | Lakes Park Botanic Garden |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 50000 | 0 | 0 | 0 | 0 | 50000 | 0 | 50000 |  | Creation of Children's garden int the Botanic Garden.
149 | CW | T, | 209260 | Player Development Complex | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 5774000 | 0 | 0 | 0 | 0 | 5774000 | 0 | 5774000 |  | Develop existing property at the Player Dev complex to include the addition of 6 new softball/youth baseball fields and lighting the existing ballfields.
150 |  |  |  | PARKS CAPITAL TOTAL |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 98012 | 442874 | 2501701 | 250126 | 3292713 | 100000 | 150456 | 250456 | 0 | 0 | 0 | 0 | 0 | 250456 | 0 | 0 |  |  | 7824000 | 150000 | 600000 | 0 | 0 | 8574000 | 3550000 | 15667169
151
152
153 |  |  |  | TOTAL CAPITAL BUDGET |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | 66117119 | 35600569 | 101217688 | #REF! | #REF! | #REF! | #REF! | #REF! | 101018655 | #REF! | #REF! | #REF! | #REF! | 97881994 | 61443921 | 71714754 | 47976986 | 38306868 | 317324523 | 543510164 | 961853342 | #REF!
[13 empty] | #REF! | #REF! | [5 empty] | #REF! | [6 empty] | #REF! | #REF!
Note on S1: bormanla: Add final expense line for 14/15 as t
Note on F7: bormanla: Change name to add SII* Source Identification & Imp
Note on AG26: bormanla: 5/29 changed per request
Note on AB52: wolfek: $3,400,000 for a loan not in One World
Note on AG52: bormanla: 4/21/15 $1,895,000 was budgeted
Note on U83: bormanla: Per Dept sheet carryovers to high
Note on U84: bormanla: Check carryovers

## August Update
REF # | MAP REF | FUNDING SOURCE | PROJ # | PROJECT NAME | PLAN | PLAN | All Prior Years | Expenses 5/6 | Expenses 6/7 | Expenses 7/8 | Expenses 8/9 | Expenses 9/10 | Expenses 10/11 | Expenses 11/12 | Expenses 12/13 | Expenses 13/14 | TOTAL PRIOR YEARS EXPENSES | BUDGET | PRELIMIN | BUDGET | $ | $ | CARRYOVER | $ | $ | CURRENT BUDGET FY 14/15 | AS OF | AS OF |  |  | BUDGET FY 15/16 | BUDGET FY 16/17 | BUDGET FY 17/18 | BUDGET FY 18/19 | BUDGET FY 19/20 | 5 YEAR BUDGET | 6-10 YEAR BUDGETS | TOTAL PROJECTED COST |  | DESCRIPTION | START UP |  | RECURRING
FUNDING SOURCE CODES: A = AD VALOREM; D = DEBT FINANCE; E = ENTERPRISE FUND; G = GRANT; GT = GAS TAX; I = IMPACT FEES; LA = LIBRARY AD VALOREM; S = SPECIAL; T = TDC; M = MSBU/TU
COMP PLAN CODES: R = REQUIRED; NR = NOT REQUIRED; F = FURTHERS SPECIFIC OR GENERALIZED REQUIREMENT OF LEE PLAN; CATEGORY CODE 1 THROUGH 5
1 |  |  |  | NATURAL RESOURCES
2 | CW | A-30155 | 208589 | Charlotte Harbor TMDL Compliance | 2 |  | 0 |  | 2190 | 12894 | 0 | 0 | 0 | 0 | 634 | 5456 | 21174 | 0 | 1493 | 1493 | [5 empty] | 1493 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1209916 | 1232583 |  | Prepare action plan & begin remedial projects in Matlacha Pass.
3 | CW | A-30100 | 208591 | Everglades-West Coast SII for TMDL Compl | 2 |  | 0 |  | 4380 | 25789 | 0 | 0 | 21920 | 105277 | 70796 | 30266 | 258428 | 0 | 585140 | 585140 | [5 empty] | 585140 | 0 | 0 |  |  | 200000 | 200000 | 200000 | 200000 | 200000 | 1000000 | 18000000 | 19843568 |  | *Source Identification and Improvements.
4 | B8 | A-30155 | 208548 | Fichter Creek Restoration | 5 |  | 0 |  | 38591 | 170556 | 176793 | 8740 | 2753 | 6290 | 0 | 0 | 403723 | 0 | 78088 | 78088 | [5 empty] | 78088 | 0 | 0 |  |  | 1400000 |  | 0 | 0 | 0 | 1400000 | 0 | 1881811 |  | Create a water conservation area through land acquisition in N Ft Myers/Alva.
5 |  | A-30100 | 208572 | Hendry Creek W Branch Water Quality Imp | [11 empty] | 0 | 0 | 400000 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 2500000 | 0 | 0 | 0 | 2500000 | 0 | 2500000 |  | Improvements to meet TMDL requirements in Hendry Creek watershed.
6 | A6 | A-30155 | 208567 | Nalle Grade Stormwater Park | 4 | [6 empty] | 0 | 0 | 403 | 34 | 101748 | 102185 | 0 | 797816 | 797816 | [5 empty] | 797816 | 0 | 0 |  |  | 0 | 3000000 | 0 | 0 | 0 | 3000000 | 0 | 3900001 |  | Provide hydrological restoration and flood relief in the Bayshore Creek watershed.
7 | C7 | A-30155 | 208557 | Sunniland/Nine Mile Run Drainage Improve | 3 | [9 empty] | 0 | 0 | 0 | 100000 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  |  | 0 | 350000 | 0 | 0 | 350000 | 0 | 350000 |  | Restore historical flows to Buckingham Trails Preserve.
8 | A5 | A-30100 | 208509 | Yellow Fever Creek Chain Improvements | 5 |  | 0 |  | 13035 | 95601 | 286 | 0 | 0 | 0 | 0 | 0 | 108922 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 571000 | 0 | 0 | 0 | 0 | 571000 | 0 | 679922 |  | Construct interconnect between Gator Slough Canal and Yellow Fever Creek in NFM and NE Cape Coral.
9 |  |  |  | NATURAL RESOURCES CAPITAL TOTAL |  |  | 0 | 0 | 58196 | 304840 | 177079 | 8740 | 24673 | 111970 | 71464 | 137470 | 894432 | 500000 | 1462537 | 1462537 | 0 | 0 | 0 | 0 | 0 | 1462537 | 0 | 0 |  |  | 2171000 | 5700000 | 550000 | 200000 | 200000 | 8821000 | 19209916 | 30387885
10 |  | A-30100 | 208573 | Natural Resources Master Project | [13 empty] | 1700000 |  | 1700000 | [5 empty] | 1700000 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
11
12 |  |  |  | SOLID WASTE
13 |  | E | 200624 | LaBelle Transfer Station Expansion | [11 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 1000000 | 3500000 | 0 | 4500000 | 0 | 4500000 |  | Expand existing LeBelle Transfer Station
14 | D10 | E | 200936 | Landfill Gas Collection System | NR |  |  |  | 0 | 16906 | 0 | 0 | 0 | 0 | 0 | 0 | 16906 | 3250000 | 0 | 3250000 | [5 empty] | 3250000 | 0 | 0 |  |  | 0 | 0 | 250000 | 300000 | 0 | 550000 | 2000000 | 5816906
15 | C7 | E | 200929 | Recycling Facility |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 250000 | 0 | 0 | 0 | 0 | 250000 | 0 | 250000 |  | Preliminary study for expansion of Recycling Facility
16 | C7 | E | 200625 | Household Chemical Waste Facility |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 500000 | 0 | 0 | 0 | 500000 | 0 | 500000 |  | Preliminary study for expansion of Household Chemical Facility
17 | C7 | E | 201007 | Waste to Energy |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 400000 | 0 | 0 | 0 | 0 | 400000 | 0 | 400000 |  | Preliminary study for expansion of WTE Facility
18 |  |  |  | SOLID WASTE CAPITAL TOTAL |  |  | 0 | 0 | 0 | 16906 | 0 | 0 | 0 | 0 | 0 | 0 | 16906 | 3250000 | 0 | 3250000 | 0 | 0 | 0 | 0 | 0 | 3250000 | 0 | 0 |  |  | 650000 | 500000 | 1250000 | 3800000 | 0 | 6200000 | 2000000 | 11466906
19
20 |  |  |  | GOVERNMENT FACILITIES
21 | CW | A, E, G48640 | 208894 | Park & Ride/Transit Stations | 3 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 136000 | 136000 | [5 empty] | 136000 | 0 | 0 |  |  | 3000000 | 0 | 0 | 1000000 | 1000000 | 5000000 | 0 | 5136000 |  | Park and Ride and Transfer Centers located east, west, north and south Lee County. | 16/17 | 160000
22 |  | S | 203416 | Tidemark Permitting Software Replace | [11 empty] | 0 | 0 | 1000000 | 0 | 1000000 | [5 empty] | 1000000 | 0 | 0 |  |  | 850000 | 0 | 0 | 0 | 0 | 850000 | 0 | 1850000 |  | Replace the permitting software. |  |  | 16/17 | 50000
23 | CW | A, G48640 | 208864 | Transit Passenger Amenities | 1 | [6 empty] | 0 | 0 | 270271 | 468549 | 507591 | 1246411 | 100000 | 771916 | 871916 | [5 empty] | 871916 | 0 | 0 |  |  | 500000 | 500000 | 500000 | 500000 | 500000 | 2500000 | 0 | 4618327 |  | Provide bus shelters, bike rakes, & ADA accessible improvements.
|  | I, 38200 | 200606 | EMS Trail Dairy | [26 empty] | 500000 |  |  |  |  | 500000 | 0 | 500000
24 |  |  |  | GOVERNMENT FACILITIES CAPITAL TOTAL |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270271 | 468549 | 507591 | 1246411 | 1100000 | 907916 | 2007916 | 0 | 0 | 0 | 0 | 0 | 2007916 | 0 | 0 | 0 |  | 4850000 | 500000 | 500000 | 1500000 | 1500000 | 8850000 | 0 | 12104327
25
26 |  |  |  | LIBRARY PROJECTS
27 |  | LA | 203627 | Two Community Libraries | [11 empty] | 0 | 0 | 2000000 | 0 | 2000000 | [5 empty] | 2000000 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
28 |  | LA | 201005 | North Ft Myers Library | [14 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 5986562.5 | 5986562.5 | 0 | 0 | 0 | 11973125 | 0 | 11973125 |  | Construct a 25,000 square ft community library | 16/17 | 600000 | 16/17 | 300000
29 |  | LA | 201006 | Bonita Springs Library | [14 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 5347812.5 | 5347812.5 | 0 | 0 | 0 | 10695625 | 0 | 10695625 |  | Construct a 25,000 square ft community library | 16/17 | 600000 | 17/18 | 310000
30 |  |  |  | LIBRARY CAPITAL TOTAL |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 |  |  | 11334375 | 11334375 | 0 | 0 | 0 | 22668750 | 0 | 24668750
31
32 |  |  |  | TRANSPORTATION DEPARTMENT
33 | B7,8 | GT,i25,A | 205075 | Alico Rd 4L - Ben Hill/Airport Rd | 5 | [6 empty] | 0 | 34703 | 663598 | 0 | 214281 | 912582 | 0 | 1672579 | 1672579 | [5 empty] | 1672579 | 0 | 0 |  |  | 0 | 0 | 11500000 | 540000 | 0 | 12040000 | 0 | 14625161 |  | Widen 2 lane rural arterial to 4 lanes. 1.78 miles |  |  | 15/16 | 45656
34 |  | I25 | 209245 | Alico Rd Connection | [12 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2240868 | 2240868 | 64000000 | 66240868 |  | Two lane arterial extension to future 4-lane road, linking Airport, FGCU more directly to Lehigh.
35 | CW | GT,I21-25 | 206002 | Bicycle/Pedestrian Facilities | 4 | 40.4.2 | 12382165 | 1151927 | 3009199 | 1692691 | 2422346 | 382378 | 31250 | 135022 | 225361 | 191171 | 18607940 | 770000 | 640905 | 1410905 | [5 empty] | 1410905 | 0 | 0 |  |  | 394000 | 2437000 | 1312000 | 843000 | 1161000 | 6147000 | 3700000 | 29865845 |  | Design & construct bike paths, lanes and sidewalks |  |  | 15/16 | 74949
36 | F6 | GT, E30720 | 205724 | Big Carlos Pass Bridge Replacement | 1 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 3500000 | 1500000 | 5000000 | [5 empty] | 5000000 | 0 | 0 |  |  | 3500000 | 3500000 | 3500000 | 3500000 | 1000000 | 15000000 | 25300000 | 45300000 |  | Replace 2 lane bascule bridge with 2 lane fixed span bridge
37 |  | GT | NEW | Big Hickory Pass Bridge Replacement | [12 empty] | 0 |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 10043000 | 10043000 |  | Replacement of existing 2-lane span bridge
38 | G7 | I-24,A,S | 205723 | Bonita Beach Road - Phase III | 5 |  |  |  | 0 | 462543 | 795030 | 234741 | 282487 | 209463 | 1080 | 0 | 1994332 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 23700000 | 25694332 |  | Widen road from 4 to 6 lanes from west of US 41 to Old 41 2.0 miles
39 | B,C4 | E30721, A, I-22, S | 204088 | Burnt Store Road Four Laning-78 to Van Buren | 5 |  | 387571 | 2175358 | 1177479 | 1583139 | 573961 | 1543038 | 592703 | 212946 | 500290 | 882743 | 9571084 | 13325000 | 1364311 | 14689311 | [5 empty] | 14689311 | 0 | 0 |  |  | 6580000 | 5042246 | 897754 | 8700000 | 630000 | 21850000 | 0 | 46110395 |  | Widen 2 lane rural arterial to 4 lanes divided road from Pine Island to Van Buren 4.86 miles |  |  | 15/16 | 8400
40 |  | E30721, | 209248 | Cape Coral Bridge WB Span Replacement | [11 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1000000 | 4000000 | 5000000 | 82500000 | 87500000 |  | Replace the westbound span fo cc bridge
41 |  | I23 | 209249 | Colonial Blvd Alternatives Analysis | [15 empty] | 0 | [5 empty] | 0 |  |  | 0 |  | 0 | 0 | 0 | 350000 | 0 | 350000 | 0 | 350000 |  | Evaluate Imp options on Colonial Blvd between McGregor and US 41
42 | B5 | GT | 205082 | Corbett Rd Widening/Resurfacing | 3 | [9 empty] | 0 | 0 | 0 | 150000 | 0 | 150000 | [5 empty] | 150000 | 0 | 0 |  |  | 690000 | 0 | 0 | 0 | 0 | 690000 | 0 | 840000 |  | Widen existing pavement to allow for 11 foot travel lanes, app bike path
43 | D6 | I23 | 200610 | Crystal Drive 2 Lane Divided | 5 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 850000 | 850000 | 1700000 | 5750000 | 7450000 |  | Reconstruct 2 lane undivided roadway to 2 lane dividied secton with bike lanes and sidewalks
44 | D6 | A | 205077 | Crystal/Plantation Roundabout | 4 | [8 empty] | 0 | 0 | 16687 | 1125 | 0 | 560339 | 560339 | [5 empty] | 560339 | 0 | 0 |  |  | 25000 | 0 | 0 | 0 | 0 | 25000 | 0 | 586464 |  | Construct roundabout
45 | E5 | GT,I-24,A | 205067 | Estero Blvd Improvements | 3 |  |  |  | 0 | 573729 | 564674 | 305276 | 59303 | 97072 | 495621 | 516584 | 2612259 | 750000 | 8419621 | 9169621 | [5 empty] | 9169621 | 0 | 0 |  |  | 7000000 | 750000 | 7300000 | 750000 | 7000000 | 22800000 | 15500000 | 50081880 |  | Imp 2 lane roadway in Town of FM Bch from Matanzas Pass to Bgd Carlos Pass |  |  | 15/16 | 39600
46 |  | GT | 209246 | Gunnery Rd/8th St Intersection Imp | [13 empty] | 0 | 0 | 0 | [5 empty] | 0 |  |  |  |  | 60000 | 850000 | 0 | 0 | 0 | 910000 | 0 | 910000 |  | Signalize the intersection and turn lane improvements
47 | C8 | I-23,A,GT | 205063 | Homestead 4L / Sunrise-Alabama | 5 |  | 0 |  | 621983 | 1138204 | 342534 | 113098 | 28928 | 20294 | 65983 | 47583 | 2362189 | 1750000 | 2730668 | 4480668 | [5 empty] | 4480668 | 0 | 0 |  |  | 13500000 | 690000 | 0 | 0 | 0 | 14190000 | 0 | 21032857 |  | Widen existing 2 lane to 4 lanes from Sunrise Blvd to Alabama Rd |  |  | 16/17 | 95020
48 | B5 | I-22 | 209247 | Kismet/Littleton Realignment | 5 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 137500 | 675000 | 825000 | 0 | 1637500 | 0 | 1637500 |  | Realignment of eastern end of Kismet to connect with Littleton
49 |  | GT | 209247 | Lee Blvd/Gunnery Rd Intersection Imp | [15 empty] | 0 | [5 empty] | 0 | 0 | 0 |  |  | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | 500000 |  | Improve congestion at intersection
50 |  | GT, A,E30720 | NEW | Little Carlos Pass Bridge Replacement | [15 empty] | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3270000 | 3270000 |  | Replacement of existing 2-lane span bridge
51 |  | GT | NEW | Little Pine Island Pass Bridge Replacment | [15 empty] | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3385000 | 3385000 |  | Replacement of existing 2-lane span bridge
52 | B7 | I-23,A | 205068 | Luckett Road 4L / Ortiz to I-75 | 5 |  | 0 |  | 0 | 538832 | 151 | 0 | 0 | 11810 | 0 | 0 | 550793 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3519000 | 4069793 |  | Widen 2 lane road to 4 lanes .46 miles
53 |  | E, GT | 200612 | New Pass Bridge Replacement | [22 empty] | 0 | 0 |  |  | 0 | 0 | 2700000 | 5000000 | 5000000 | 12700000 | 7060000 | 19760000 |  | Replacement of existing 2-lane span bridge
54 | C6 | A, I-23 | 204100 | North Airport Road Extension West | 4 |  |  |  | 0 | 0 | 0 | 1350 | 235718.25 | 100358.15 | 92114.36 | 18283.5 | 447824.26 | 4195000 | 277177 | 4472177 | [5 empty] | 4472177 | 0 | 0 |  |  | 70000 | 0 | 0 | 0 | 0 | 70000 | 0 | 4990001.26 |  | Extend existing 2 lane east to Metro |  |  | 15/16 | 14524
55 | C7 | I-23,A |  | Ortiz 4L / Colonial-MLK | 5 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 1550000 | 0 | 0 | 1550000 | 13269000 | 14819000 |  | Widen 2 lane to 4 lane 1.73 miles
56 | C7 | I-23,A | 205056 | Ortiz Avenue/SR80 - Luckett | 5 |  | 0 | 368814 | 2660268 | 2282520 | 1829137 | 643708 | 620568 | 1269 | 7432 | 920 | 8414636 | 0 | 3143703 | 3143703 | [5 empty] | 3143703 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 12450000 | 24008339 |  | Widen 2 lane to 4 lane 1.33 miles
57 | C7 | I-23,A | 204072 | Ortiz Four Laning - MLK to Luckett | 5 | 37.1 POL 36.1.5 | 78974 | 1301297 | 3377302 | 2110669 | 1516558 | 240660 | 115320 | 352093 | 65158 | 42840 | 9200871 | 0 | 604811 | 604811 | [5 empty] | 604811 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 9325000 | 19130682 |  | Widen 2 lane to 4 lane 1.25 miles
58 |  | S, GT | 205081 | Palomino Lane Improvements | [11 empty] | 0 | 0 | 0 | 132614 | 132614 | [5 empty] | 169636 | 0 | 0 |  |  | 80364 | 1700000 | 0 | 0 | 0 | 1780364 | 0 | 1950000 |  | Improvement to existing 2 lane collector road, bike path.
59 | CW | GT | 206759 | Signal System ATMS Upgrades | 3 | [6 empty] | 0 | 0 | 623277 | 800312.82 | 644528 | 2068117.82 | 750000 | 205925 | 955925 | [5 empty] | 955925 | 0 | 0 |  |  | 750000 | 750000 | 750000 | 750000 | 750000 | 3750000 | 0 | 6774042.82 |  | Upgrade existing traffic signal system |  |  | 15/16 | 9500
60 |  | GT | 200614 | Sunshine Blvd/8th St SW Roundabout | [13 empty] | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 200000 | 200000 | 550000 | 950000 | 0 | 950000 |  | Construct roundabout
61 | D7 | I-24,A,GT | 204053 | Three Oaks Pkwy Extension, North | R | 36.1.1;36.1.4 | 1990373 | 79909 | 208499 | 3482379 | 608014 | 50814 | 361087 | 149075 | 6488 | 0 | 6936638 | 0 | 5690477 | 5690477 | [5 empty] | 5690477 | 0 | 0 |  |  | 0 | 0 | 3000000 | 0 | 3000000 | 6000000 | 37250000 | 55877115 |  | 4 lane arterial extension from north of Alico to Daniels 3.5 miles
62 | C5,E4 | E | 205818 | Toll Interoperability | 3 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 150000 | 150000 | [5 empty] | 150000 | 0 | 0 |  |  | 150000 | 150000 | 150000 | 150000 | 150000 | 750000 | 0 | 900000 |  | Upgrade software & hardware
63 | C5,E4 | E |  | Toll System Replacement | NR |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 2250000 | 2250000 | 0 | 0 | 4500000 | 0 | 4500000 |  | Replace Leeway Service Center ARCS system.
64 |  |  |  | TRANSPORTATION CAPITAL TOTAL |  |  | 14839083 | 5077305 | 11054730 | 13864706 | 8652405 | 3515063 | 2362067.25 | 2576277.15 | 2259840.18 | 2575620.5 | 63680391.08 | 25190000 | 27093130 | 52283130 | 0 | 0 | 0 | 0 | 0 | 52320152 | 0 | 0 |  |  | 33299364 | 18256746 | 35784754 | 23458000 | 26331868 | 137130732 | 320021000 | 573152275.08
65
66 |  |  |  | UTILITIES
67 | E7 | E | 207614 | Alico Rd 4L-Ben Hill/Airport Haul-WM Reloc | 3 | [8 empty] | 0 | 0 | 3497 | 3497 | 0 | 196320 | 196320 | [5 empty] | 196320 | 0 | 0 |  |  | 0 | 0 | 3750000 | 0 | 0 | 3750000 | 0 | 3949817 |  | Relocate existing water main.
68 | C6 | E |  | Bayshore Rd 24" WM-Samville to N. Tamiami | 5 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3450000 | 3450000 |  | Install 13,400 LF of 24 " water main from Samville Rd to N Tamiami Trail.
69 | E7 | E | 207334 | Ben Hill Griffin Force Main Improve South | 5 | [9 empty] | 0 | 0 | 0 | 425000 | -425000 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 450000 | 250000 | 4950000 | 0 | 0 | 5650000 | 0 | 5650000 |  | Force main improvements along Ben Hill Griffin Parkway S of FGCU Parkway to the Pinewoods WTP.
70 | C7 | E |  | Colonial 30" Water Main-Ortiz to Gumnnery | 5 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 8400000 | 8400000 |  | Install 33,000 LF of 24" water main from Ortiz to Gunnery Rd.
71 |  | E |  | Corkscrew Groundwater ASR System | [11 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 21970000 | 21970000 |  | Additional raw water spply source for utilization by Corkscrew & Geen Meadows WTP
72 |  | E | 207622 | Corkscrew Production Well Panal Rep | [11 empty] | 0 | 0 | 1170240 | 0 | 1170240 | [5 empty] | 1170240 | 0 | 0 |  |  | 1250000 | 0 | 0 | 0 | 0 | 1250000 | 0 | 2420240 |  | Replace production well panel to control flow rates.
73 | CW | E | 207448 | County-Wide Fiber Network | 1 | [8 empty] | 0 | 88510 | 172788 | 261298 | 100000 | 88702 | 188702 | [5 empty] | 188702 | 0 | 0 |  |  | 100000 | 50000 | 50000 | 25000 | 25000 | 250000 | 100000 | 800000 |  | Install network for LCU facilities across the county.
74 |  | E | 207307 | Daniels Pkwy Forcemain Ext to Gateway | [31 empty] | 0 | 2250000 |  |  | Construct a new Force Main along Daniels Parkway.
75 | E5 | E | 200617 | FMB Deep Injection Well - #2 | 5 | OBJ 54.1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 400000 | 0 | 6000000 | 6400000 | 0 | 6400000 |  | Install a deep injection well at FMBWWTP as required by FDEP.
76 | A5 | E | 207606 | Del Prado Water Main Replacement | 3 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 200000 | 1075000 | 0 | 0 | 0 | 1275000 | 0 | 1275000 |  | Replace existing 16" PVC water main.
77 | CW | E | 207416 | DOT Project Utility Relocations | 3 |  | 509542 | 354823 | 13105 | 368506 | 340282 | 334484 | 213047 | 326053 | 54111 | 6230 | 2520183 | 0 | 147078 | 147078 | [5 empty] | 147078 | 0 | 0 |  |  | 100000 | 0 | 0 | 0 | 0 | 100000 | 0 | 2767261 |  | Misc FDO & LCDOT relocating of lines for roadway pjts
78 | CW | E | 207429 | Electrical Equipment Upgrades & Replacements | 3 |  | 314042 | 174091 | 168057 | 132422 | 567577 | 180315 | 640281 | 575575 | 108256 | 208452 | 3069068 | 536100 | 202619 | 738719 | [5 empty] | 738719 | 0 | 0 |  |  | 510400 | 233800 | 120000 | 70000 | 70000 | 1004200 | 3300000 | 8111987 |  | Replace old electrical equipment and upgrade equipment to meet new load demands.
79 | CW | E | 207446 | Energy Management Initiatives Program | NR | [6 empty] | 0 | 54065 | 135695 | 34134 | 85181 | 309075 | 100079 | 32869 | 132948 | [5 empty] | 132948 | 0 | 0 |  |  | 100000 | 100000 | 100000 | 25000 | 25000 | 350000 | 100000 | 892023 |  | Purchase power monitoring equipment.
80 | E5, F5 | E | 207326 | Estero Blvd Force Main Relocation | 3 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 19595 | 19595 | 150000 | 1011394 | 1161394 | [5 empty] | 1161394 | 0 | 0 |  |  | 1450000 | 150000 | 1450000 | 150000 | 1450000 | 4650000 | 1725000 | 7555989 |  | Relocate force main to allow for construction of roadway improvements.
81 | CW | E | 207447 | Facility Wide Security System | 2 | [7 empty] | 0 | 3292 | 18051 | 23089 | 44432 | 25000 | 48155 | 73155 | [5 empty] | 73155 | 0 | 0 |  |  | 75000 | 75000 | 25000 | 25000 | 25000 | 225000 | 175000 | 517587 |  | Install cameras, gates, entrance systems at all facilities.
82 | CW | E | 207613 | Fiber Optic Upgrades | 3 | [5 empty] | 0 | 0 | 0 | 76601 | 206033 | 105690 | 388324 | 0 | 626341 | 626341 | [5 empty] | 626341 | 0 | 0 |  |  | 2900000 | 0 | 0 | 0 | 0 | 2900000 | 0 | 3914665 |  | Install fiber optics to each well and tie into the plant PLC.
83 | D5 | E | 207293 | Fiesta Village Sewer Collection System Improve | 5 |  | 0 | 108 | 5826 | 31578 | 0 | 0 | 0 | 0 | 0 | 0 | 37512 | 650000 | -650000 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 150000 | 950000 | 0 | 0 | 0 | 1100000 | 0 | 1137512 |  | Replace ctrl system
84 |  | E | 209250 | Fiesta Village WWTP Control Sys Upgrade |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | 0 | 0 |  |  | 100000 | 850000 | 0 | 0 | 0 | 950000 | 0 | 950000 |  | Construct a new master lift station.
85 | D5 | E | 200616 | Fiesta Village WWTP RM Upgrade | 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 300000 | 100000 | 4325000 | 0 | 4725000 | 0 | 4725000 |  | Site selection, engineering design, permitting, bidding and construction of one Class I underground injection ctol deep injection well
86 |  | E | 209251 | Fiesta Village WWTP Deep Injection Well |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 462500 | 6900000 | 0 | 0 | 0 | 7362500 | 0 | 7362500 |  | Upgrade the reuse system to increase reuse flow capacity.
87 | D5 | E | 207450 | Fiesta WWTP Sludge Handling | 1 |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 850000 | -850000 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 150000 | 950000 | 0 | 0 | 0 | 1100000 | 0 | 1100000 |  | Design and construct permanent dewatering equipment.
88 |  | E | NEW | FMB Main Switchgear Replacement | [11 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 232000 | 1542000 | 0 | 0 | 1774000 | 0 | 1774000 |  | Replace the existing pre-stressed Equalization tank, pumps and dome.
89 | E5 | E | 207451 | FMB WWTP Controls System Replacement | 3 | [9 empty] | 0 | 0 | 0 | 0 | 600000 | 600000 | [5 empty] | 600000 | 0 | 0 |  |  | 700000 | 0 | 0 | 0 | 0 | 700000 | 0 | 1300000 |  | Replace main switchgear
90 | E5 | E | 200626 | FMB WWTP EQ Tank Replacement | 3 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 480000 | 8200000 | 0 | 8680000 | 0 | 8680000 |  | Replace obsolete ctrl system of WWTP with new PLC system
91 |  | E | 200620 | Gateway WWTP Sludge Dewatering System Roof | [22 empty] | 0 | 0 |  |  | 0 | 65000 | 0 | 0 | 0 | 65000 | 0 | 65000 |  | Provide covered building for storage and operation of centrifuge.
92 | CW | E | 207247 | Inflow & Infiltration Improvement | 3 |  | 1175459 | 179309 | 238543 | 670947 | 704876 | 1569487 | 1342580 | 427224 | 1354610 | 455689 | 8118724 | 500000 | 239892 | 739892 | [5 empty] | 739892 | 0 | 0 |  |  | 500000 | 500000 | 500000 | 500000 | 500000 | 2500000 | 2000000 | 13358616 |  | Rehab gravity lines & pump stations which cause inflow and infiltration.
93 | CW | E | 207430 | Instrumentation Upgrades & Improvements | 3 |  | 666455 | 184929 | 86731 | 10467 | 183361 | 152678 | 129714 | 78521 | 0 | 92594 | 1585450 | 115100 | 6110 | 121210 | [5 empty] | 121210 | 0 | 0 |  |  | 202500 | 150000 | 150000 | 100000 | 100000 | 702500 | 600000 | 3009160 |  | Install new equip as needed to improve control & meet standards and specifications.
94 | E7 | E |  | Interconnect Pinewoods Distribution Sys | 3 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 4850000 | 4850000 |  | Install 19,000 LF of watermain from Corkscrew Rd to Airport Haul Reservoir.
95 | CW | E | 207444 | LCU Generator Replace & Improve | 3 |  |  |  |  | 0 | 0 | 14405 | 67963 | 638269 | 100335 | 391268 | 1212240 | 340000 | 19185 | 359185 | [5 empty] | 359185 | 0 | 0 |  |  | 348000 | 198000 | 0 | 0 | 0 | 546000 | 1000000 | 3117425 |  | Purchase new generators as needed.
96 |  | E | 209272 | Mariana Ave WM Replacement | [12 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 60000 | 500000 | 0 | 0 | 0 | 560000 | 0 | 560000 |  | Replace appr 5000LF of existing 2" & 6" water main along Mariana Ave
97 |  | E | 207335 | Master Lift Station 7716 Improvements | [11 empty] | 0 | 0 | 800000 | -800000 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 825000 | 1425000 | 0 | 0 | 0 | 2250000 | 0 | 2250000 |  | Replace with a new station at a new location.
98 |  | R | 200621 | McGregor-Tanglewood Force Main Rep | [12 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 440000 | 2900000 | 0 | 0 | 3340000 | 0 | 3340000 |  | Replace24" DIP force main along McGregor from N Whiskey Ck Bridege to Tanglewood
99 | D5 | E | 207453 | McGregor Blvd Water Main Replacement | 3 | [8 empty] | 0 | 0 | 0 | 0 | 2000000 | 900000 | 2900000 | [5 empty] | 2900000 | 0 | 0 |  |  | 4000000 | 0 | 0 | 0 | 0 | 4000000 | 0 | 6900000 |  | Replace existing water main with a new 12" water main. From College Parkway to Whiskey Creek Bridge.
100 | B7 | E | 207618 | NLC WTP Deep Injection Well Backup | 3 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 425000 | 5350000 | 0 | 0 | 5775000 | 0 | 5775000 |  | Install a backup Deep Injection Well.
101 | A7 | E | 207619 | North Lee County WTP Expansion to 15 MGD | 5 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2300000 | 0 | 2300000 | 28300000 | 30600000 |  | Expand the existing NLC WTP from 10 to 15 MGD.
102 | A7 | E | 207619 | NLC WTP Wellfield Expansion to 15 MGD | 5 | [9 empty] | 0 | 1013 | 1013 | 0 | 250000 | 250000 | [5 empty] | 250000 | 0 | 0 |  |  | 0 | 0 | 0 | 2618986 | 0 | 2618986 | 10580000 | 13449999 |  | Construct 6 additional lower Hawthorn production wells.
103 | C7,D7 | E |  | North-South 30" Water Main-SR80 to AHR | 3,5 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 28200000 | 28200000 |  | Install 74,000 LF of 30" water main along Buckingham Rd from SR 82 to end at the Airport Haul Reservoir.
104 | B5.B6 | E |  | N Tamiami 24" WM-Pondella to Cleveland | 5 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 5600000 | 5600000 |  | Install 22,000 LF of 24" water main along N Tamiami Trail from Pondella Rd to Cleveland Avenue.
105 |  | E | 209267 | Olga WTP MCC Replacement | [11 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 500000 | 500000 | 0 | 0 | 0 | 1000000 | 0 | 1000000 |  | Replace motor control one & motor control two over a 2 year period.
106 | B6 | E | 207454 | Operations Building Replacement | 3 | [9 empty] | 0 | 0 | 0 | 150000 | -150000 | 0 | [5 empty] | 0 | 0 | 0 | 75000 |  | 75000 | 0 | 0 | 0 | 0 | 75000 | 2500000 | 2575000 |  | Construct a new building for Utilities Operations.
107 | B5 | E | 209268 | Orange Grove WM-Pondella to Hancock | 3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 100000 | 700000 | 0 | 0 | 800000 | 0 | 800000 |  | Construct a 12" water main along Orange Grove Blvd. to Hancock Bridge Parkway.
108 | B7 | E |  | Ortiz FM - Palm Beach to Ballard | 3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2150000 | 2150000 |  | Replace the aging and failing sewer force main along Ortiz Avenue.
109 | B7 | E |  | Ortiz Ave Utility Relocation-MLK to SR80 | 3 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 6000000 | 6000000 |  | Relocate existing utilities in conflict with the proposed roadway.
110 | D6 | E | 207127 | Page Park Waterline Improvements | 3 |  | 0 |  | 0 | 9287 | 0 | 0 | 0 | 0 | 58487 | 154209 | 221983 | 1300000 | 443784 | 1743784 | [5 empty] | 1743784 | 0 | 0 |  |  | 4100000 | 0 | 0 | 0 | 0 | 4100000 | 0 | 6065767 |  | Replace old cast iron & small pipes in the Page Park area.
111 | D3 | E | 207238 | Pine Island Sewer Transmission System | 5 |  | 27767 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 27767 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4027767 |  | Install a main from Pine Island Road to Bookelia and construct a master lift station.
112 | D3 | E | 207239 | Pine Island WWTP Expansion | 5 |  | 403481 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 403481 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 6500000 | 6903481 |  | Expand Pine Island Wastewater Treatment Plant to 1 MGD.
113 |  | E | 209269 | Pine Ridge FM-FMB WWTP/Gulf Reflections | [11 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 230000 | 200000 | 1533000 | 0 | 0 | 1963000 | 0 | 1963000 |  | Replace 4,000 ft of force main along Pine Ridge Rd from FMB WWTP to Gulf Reflection Drive.
114 | F7 | E | 200627 | Pinewoods Odor Control Scrubber | 3 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 200000 | 0 | 0 | 0 | 200000 | 0 | 200000 |  | Install a redundant odor control scrubber system.
115 | F7 | E | 200623 | Pinewoods WTP Degasifiers Replacement | 3 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 759000 | 0 | 0 | 0 | 759000 | 0 | 759000 |  | Replace 3 leaking degasifier units.
116 | D5 | E | 207284 | Reclaim Water ASR | 5 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 1260000 | 0 | 4500000 | 0 | 0 | 5760000 | 0 | 5760000 |  | Construction of a reclaimed water ASR.
117 | CW | E | 207455 | Reuse System & Site Improvements | 3 | [9 empty] | 0 | 57160 | 57160 | 0 | 447645 | 447645 | [5 empty] | 447645 | 0 | 0 |  |  | 0 | 1500000 | 1500000 | 0 | 0 | 3000000 | 0 | 3504805 |  | Install equipment replacements and upgrades.
118 | E7 | E | 207162 | San Carlos Blvd Improv-Linda Loma to Kelly | 3 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1800000 | 1800000 |  | Replace 14" water main with a 16" water main, from just north of Summerlin Road to Kelly Road.
119 | CW | E | 207424 | SCADA Upgrades & Improvements | 3 |  | 586870 | 223717 | 170815 | 222618 | 307965 | 7668 | 164024 | 181483 | 249714 | 556144 | 2671018 | 700000 | 405674 | 1105674 | [5 empty] | 1105674 | 0 | 0 |  |  | 400000 | 400000 | 300000 | 200000 | 200000 | 1500000 | 1500000 | 6776692 |  | Install new & upgrade SCADA equipment though out the system.
120 | CW | E | 207456 | Secondary Containments-Chemical Tanks | 3 | [9 empty] | 0 | 38048 | 38048 | 0 | 144313 | 144313 | [5 empty] | 144313 | 0 | 0 |  |  | 150000 | 150000 | 150000 | 400000 | 0 | 850000 | 0 | 1032361 |  | Adding Secondary containment areas to each of chemical tanks at WWTP
121 | CW | E | 207184 | SFM Water Transmission Line Improvements | 5 |  | 0 |  | 0 | 132553 | 110241 | 16077 | 29635 | 41454 | 0 | 0 | 329960 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 200000 | 2000000 | 2200000 | 0 | 2529960 |  | Install 16" water main along Crystal Drive and 12" water main along Winkler Road.
122 | C6 | E | 207194 | Summerlin Road Water System Improvements | 5 |  | 0 |  | 0 | 34752 | 343135 | 99179 | 29275 | 13181 | 0 | 0 | 519522 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 6379248 | 6898770 |  | Install water main in the Summerlin & Winkler area.
123 | E7 | E | 207325 | Three Oaks Oxidation Ditch Improvements | 4 | [7 empty] | 0 | 0 | 77422 | 564631 | 642053 | 17000000 | 1330002 | 18330002 | [5 empty] | 18093947 | 0 | 0 |  |  | 10864855 | 0 | 0 | 0 | 0 | 10864855 | 0 | 29600855 |  | Provides additional air to the oxidation ditches.
124 | E7 | E |  | Three Oaks WWTP Expansion to 8 MGD | 5 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 28000000 | 28000000 |  | Expand the plant to 8 MGD.
125 | B7 | E | 207164 | Tice Street Loop | 3 |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 56225 | 31249 | 87474 | 0 | 13065 | 13065 | [5 empty] | 13065 | 0 | 0 |  |  | 900000 | 0 | 0 | 0 | 0 | 900000 | 0 | 1000539 |  | Install water lines in the Tice area to complete the connection of the water distribution system.
126 | D7 | E |  | Treeline WM-Terminal Access to Daniels | 5 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 4430000 | 4430000 |  | Construct a 30" water transmission line along Treeline.
127 | B5 | E | 207170 | US 41 Watermain Improvement | 3 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 217967 | 1397271 | 293295 | 1908533 | 3800000 |  | 3800000 | [5 empty] | 3800000 | 0 | 0 |  |  | 2500000 | 0 | 0 | 0 | 0 | 2500000 | 0 | 8208533 |  | Replace 10" water main along US 41 from Alico Road to Cypress Lake Dr.
128 | CW | E | 207229 | Wastewater System Improvements | 3 |  | 479528 | 468821 | 196524 | 85350 | 172861 | 242399 | 237657 | 225803 | 229409 | 335737 | 2674089 | 250000 | 1327 | 251327 | [5 empty] | 251327 | 0 | 0 |  |  | 250000 | 250000 | 250000 | 250000 | 250000 | 1250000 | 1000000 | 5175416 |  | County-wide equipment replacement within wastewater system.
129 | CW | E | 207138 | Wastewater Treatment Plant Improvements | 1 |  | 1125126 | 171618 | 213466 | 488549 | 221710 | 35460 | 943665 | 115298 | 93393 | 566110 | 3974395 | 380000 | 533776 | 913776 | [5 empty] | 913776 | 0 | 0 |  |  | 370000 | 245000 | 500000 | 0 | 0 | 1115000 | 2900000 | 8903171 |  | County-wide replacement/improvements to the wastewater plants.
130 | CW | E | 207094 | Water System Improvements | 3 |  | 523350 | 127468 | 10190 | 56792 | 283756 | 951690 | 483900 | 457779 | 575264 | 509225 | 3979414 | 250000 | 283522 | 533522 | [5 empty] | 533522 | 0 | 0 |  |  | 500000 | 500000 | 500000 | 500000 | 500000 | 2500000 | 1000000 | 8012936 |  | County-wide equipment improvements within the water system.
131 | D7 | E | 207193 | Water Transmission Ben Hill To Treeline | 5 |  | 0 | 39031 | 2491114 | 249191 | 288202 | 19465 | 82460 | 7936 | 45477 | 131874 | 3354750 | 0 | 179607 | 179607 | [5 empty] | 179607 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 6960000 | 10494357 |  | Install water transmission lines from Fiddlesticks to Old Gladiolus.
132 | CW | E | 207268 | Water Treatment Plant Improvements | 1 |  | 837185 | 429675 | 287247 | 248580 | 78439 | 1159839 | 1551050 | 661203 | 163138 | 394560 | 5810916 | 180600 | 306069 | 486669 | [5 empty] | 486669 | 0 | 0 |  |  | 90000 | 0 | 0 | 0 | 0 | 90000 | 0 | 6387585 |  | County-wide replacement/improvements to the water plants.
133 | E7 | E | 207426 | Water/Sewer Line Relocation-Three Oaks Ext. | 3 |  | 250 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 300500 |  | Relocate water and sewer lines along Fiddlesticks Blvd.
134 | CW | E | 207149 | Well Redevelopment/Upgrade & Rebuild | 3,5 |  | 678714 | 79716 | 232330 | 597002 | 760980 | 611615 | 562164 | 256663 | 302838 | 385 | 4082407 | 130000 | 404081 | 534081 | [5 empty] | 534081 | 0 | 0 |  |  | 130000 | 130000 | 130000 | 130000 | 130000 | 650000 | 710000 | 5976488 |  | Upgrade, reconstruct & replace old wells through out the system.
135 |  | E | 209270 | Winkler Road Watermain Improvement | [11 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 200000 | 2100000 | 0 | 0 | 0 | 2300000 | 0 | 2300000 |  | Install 12" water main from Cypress Lake Dr to McGregor Blvd.
136 | C5 | E | 207183 | Waterway Estates Water Transmission Line Imp | 5 |  | 0 |  | 72350 | 119076 | 11669 | 12050 | 28144 | 10835 | 0 | 0 | 254124 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 150000 | 1100000 | 0 | 0 | 1250000 | 0 | 1504124 |  | Construction of a 12" Water Main on Pondella Rd
137 | C6 | E | 207620 | Work Dr Industrial Pk WM Improvements | 3,4 | [9 empty] | 0 | 0 | 0 | 2075000 | 0 | 2075000 | [5 empty] | 2075000 | 0 | 0 |  |  | 600000 | 2000000 | 0 | 0 | 0 | 2600000 | 0 | 4675000 |  | Upgrade existing water main along Cargo St and Katanga Ct in our service area of the City of Ft Myers.
138 | C6 | E | 200607 | LCU Billing System | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 700000 | 2000000 | 0 | 0 | 0 | 2700000 | 0 | 2700000 |  | New software system. |  |  | 16/17 | 1000000
139 |  |  |  | UTILITIES CAPITAL TOTAL |  |  | 7327769 | 2433556 | 4186298 | 3457670 | 4375054 | 5406811 | 6559624 | 4450832 | 5212678 | 5197713 | 48608005 | 33977119 | 5986530 | 39963649 | 0 | 0 | 0 | 0 | 0 | 39727594 | 0 | 0 |  |  | 38453255 | 27002800 | 33030000 | 20018986 | 11275000 | 129780041 | 198729248 | 414594888
140
141 |  |  |  | PARKS - COMMUNITY & REGIONAL
142 | C6 | I-24 | 202146 | Brooks Park Master Plan & Improvements | 5 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | -95 | 0 | -95 | 0 | 53856 | 53856 | [5 empty] | 53856 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1250000 | 1303761 |  | Prepare a master plan for Brooks Park & construct a parking lot, clubhouse and restrooms.
143 | A8 | I-R | 202153 | Caloosahatchee Reg Pk Maint Building | 3 | [9 empty] | 0 | 3400 | 3400 | 0 | 96600 | 96600 | [5 empty] | 96600 | 0 | 0 |  |  | 250000 | 0 | 0 | 0 | 0 | 250000 | 0 | 350000 |  | Construct a maint at Caloosahatchee Reg Park.
144 | CW | I-R | 202154 | Greenways | 5 | [8 empty] | 0 | 0 | 0 | 0 | 100000 | 0 | 100000 | [5 empty] | 100000 | 0 | 0 |  |  | 0 | 150000 | 600000 | 0 | 0 | 750000 | 1150000 | 2000000 |  | Construct Greenways and Blueways. Project - Able Canal in Lehigh
145 | B8 | I - R |  | Idalia Park | 5 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 |  | Development of a passive park on the Caloosahatchee River.
146 |  | I-23 | 201865 | Lehigh Park Acquisition & Improvements | 3 | [6 empty] | 0 | 98012 | 442874 | 2501796 | 246726 | 3289408 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | 4789408 |  | Continuation of park improvements in Lehigh. 30-acres along Joal Blvd.
147 | B2 | A |  | Pine Island Comm Marina Mstr Plan & Impr | 3 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1050000 | 1050000 |  | Improvements to the property at the marina.
148 | D5 | A | 209266 | Terry Park Main/Storage Bldg |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 250000 | 0 | 0 | 0 | 0 | 250000 | 0 | 250000 |  | Replace storage building for equipment.
149 | D5 | I-R | 209265 | Lakes Park Botanic Garden |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 50000 | 0 | 0 | 0 | 0 | 50000 | 0 | 50000 |  | Creation of Children's garden int the Botanic Garden.
150 |  | A | 209271 | Lynn Hall Park Boardwalk & Dune Imp | [12 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 70000 | 0 | 0 | 0 | 0 | 70000 | 0 | 70000 |  | The cost to construct the boardwalk and dune walkovers
151 | CW | T, | 209260 | Player Development Complex | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | 5774000 | 0 | 0 | 0 | 0 | 5774000 | 0 | 5774000 |  | Develop existing property at the Player Dev complex to include the addition of 6 new softball/youth baseball fields and lighting the existing ballfields.
152 |  |  |  | PARKS CAPITAL TOTAL |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 98012 | 442874 | 2501701 | 250126 | 3292713 | 100000 | 150456 | 250456 | 0 | 0 | 0 | 0 | 0 | 250456 | 0 | 0 |  |  | 7894000 | 150000 | 600000 | 0 | 0 | 8644000 | 3550000 | 15737169
153
154
155 |  |  |  | TOTAL CAPITAL BUDGET |  |  | 22166852 | 7510861 | 15299224 | 17644122 | 13204538 | 8930614 | 9044376.25 | 7852224.15 | #REF! | #REF! |  | 66117119 | 35600569 | 101217688 | #REF! | #REF! | #REF! | #REF! | #REF! | 101018655 | #REF! | #REF! | #REF! | #REF! | 98651994 | 63443921 | 71714754 | 48976986 | 39306868 | 322094523 | 543510164 | 1082112200.08 | #REF!
[13 empty] | #REF! | #REF! | [5 empty] | #REF! | [6 empty] | #REF! | #REF!
Note on S1: bormanla: Add final expense line for 14/15 as t
Note on F7: bormanla: Change name to add SII* Source Identification & Imp
Note on AG26: bormanla: 5/29 changed per request
Note on F28: bormanla: No sheet entered per Pete
Note on AB52: wolfek: $3,400,000 for a loan not in One World
Note on AG52: bormanla: 4/21/15 $1,895,000 was budgeted
Note on U83: bormanla: Per Dept sheet carryovers to high
Note on U84: bormanla: Check carryovers