## Sheet1
SUMMARY OF MAJOR ROAD PROJECTS PROGRAMMED BY LEE COUNTY - FY21/22-25/26
FY 98-20
COMM | PROJ. |  |  | PRIOR | 20/21 | [5 empty] | 5-YEAR |  | PROJECT | REVENUE | PROJECT
DIST. | # | PROJECT NAME | DRIVER | EXP. | BUDGET | 21/22 | 22/23 | 24/24 | 24/25 | 25/26 | TOTAL | 6-10 | TOTAL | SOURCE | MANAGER
MAJOR PROJECTS
2,5 | 209245 | Alico Rd. Connector/Alico Rd. to SR 82 opposite Sunshine Blvd. | People-to-jobs link, | 6180573 | 12397200 | 0 | 0 | 10759314 | 0 | 0 | 10759314 | 106540155 | 135877242 | IF 25 | Vince Miller
|  |  | Daniels Pkwy. relief | ROW | ROW/DES |  |  | DES/CST | [5 empty] | GT | vmiller@leegov.com
|  |  | NM - Core Critical | [10 empty] | Debt
All | 206002 | Bicycle/Pedestrian Facilities | Implementation of bike- | [10 empty] | IF/GT | Tom Marquardt
|  | Annual project for facilities on existing County-maintained roads | ped plan, BPAC prior- | [11 empty] | tmarquardt@leegov.com
ities, Complete Streets
|  | Specific Projects: | principals
1 |  | Veterans Pkwy.SW 10th St. to Skyline Blvd. | 2016 Priority #22 |  | 40500 | 232850 | 0 | 0 | 0 | 0 | 273350 |  | 313850 | IF22
[5 empty] | DES/SUR | CST/CEI
1 |  | Veterans Pkwy.SW 3rd Pl to SW 2nd Ave | 2016 Priority #23 |  | 44910 | 258225 | 0 | 0 | 0 | 0 | 303135 |  | 348045 | IF22
[5 empty] | DES/SUR | CST/CEI
|  | Hancock Bridge Pkwy Orange Grove to 4055 Hancock | 2017 Priority #4 |  |  | 495000 | 0 | 546250 | 0 | 0 | 1041250 |  | 1041250 | IF22
[6 empty] | ROW |  | CST/CEI
DES/SUR
|  | Hancock Bridge Pkwy | 2020 Priority #13 |  |  | 137293 |  | 789433 |  |  | 926726 |  | 926726 | IF22
|  | Hunter Blvd - Orange Grove |  |  |  | DES/SUR |  | CST/CEI
|  | Plantation | 2019 Priority #2 |  |  | 0 | 1369367 | 0 | 6846833 | 0 | 8216200 |  | 8216200 | GT
|  | Daniels - Idlewild |  |  |  |  | DES/SUR
5 |  | Orange River Blvd. Palm Beach Blvd. to Lorraine Dr. | 2016 Priority #4 |  |  | 1354571 |  | 2268782 | 0 | 0 | 3623353 |  | 3623353 | GT
[6 empty] | DES/SUR |  | CST/CEI | [5 empty] | GT
5 |  | Tice St. Sidewalk/South Side, Ortiz to SR 80 | 2015 Priority #2 |  | 268513 | 1543947 | 0 | 0 | 0 | 0 | 1543947 |  | 1812460 | IF23
[5 empty] | DES/SUR | CST/CEI
5 |  | Bell Blvd. SR 82 to Sunrise | 2016 Priority #3 |  |  | 623080 | 0 | 3557183 | 0 | 0 | 4180263 |  | 4180263 | GT
[6 empty] | DES/SUR/ROW | 0 | CST/CEI | 0
|  | Westgate N Lee-Sunshine | 2017 Priority #2 |  |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 | IF23
[9 empty] | DES/SUR |  |  | CST/CEI
|  | Westgate S Lee-Sunshine | 2017 Priority #3 |  |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 | IF23
[9 empty] | DES/SUR |  |  | CST/CEI
|  | Bell Blvd Sunrise to Joel | 2016 Priority #3 |  |  | 0 | 398688 | 0 | 2290078 | 0 | 2290078 |  | 2290078 | FDOT
[7 empty] | DES/SUR |  | CST/CEI
|  | Westgate Blvd. East Lee -4th St | 2020 Priority #3 |  |  | 0 | 0 | 128138 | 0 | 736799 | 864937 |  | 864937 | IF23
[8 empty] | DES/SUR |  | CST/CEI
2 |  | Alico Rd. Sidewalk/North Side, RR Crossing to Quaker Ln. | 2015 Priority #27 |  |  | 1139782 | 0 | 1091247 | 0 | 0 | 2231029 |  | 2231029 | IF24
[6 empty] | DES/SUR/ROW |  | CST/CEI | 0
4 |  | Pine Rd. Allaire Ln to US 41 | 2016 Priority #28 |  |  | 0 | 0 | 135801 | 780858 | 0 | 916659 |  | 916659 | IF24
[8 empty] | DES/SUR | CST/CEI
|  | Pine Ridge Rd. Stevens-Summerlin | 2017 Priority #12 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | IF24
3 |  | Jetport Loop Allaire Ln - US 41 | 2020 Priority #97 |  |  | 0 | 138793 | 0 | 798057 | 0 | 936850 |  | 936850 | IF24
[7 empty] | DES/SUR |  | CST/CEI
|  | Pine Ridge Rd San Carlos - Summerlin | 2020 Priority #5 |  |  |  |  | 337511 |  | 1940688 | 2278199 |  | 2278199 | IF25
[8 empty] | DES/SUR |  | CST/CEI |  |  |  | GT
3 | 205724 | Big Carlos Pass Bridge | Age Condition of bridge | 4012244 | 5008972 | 45137536 | 0 | 0 | 0 | 0 | 45137536 |  | 54158752 | Sanibel | Tom Marquardt
|  |  | (Bridge Health Index) | PD&E Study | PD&E Study | CST/CEI | [7 empty] | SURP. | tmarquardt@leegov.com
TOLLS
|  |  | Mandated |  | DES/CST | [8 empty] | DEBT
1,2 | 209248 | Cape Coral Bridge WB Span Replacement | Age/condition, escalating | 0 | 0 | 13148702 | 0 | 0 | 0 | 0 | 13148702 | 111808571 | 124957273 | CAPE/MP | Tom Marquardt
|  |  | maintenance costs |  |  | DES | DES |  |  |  |  | CST/CEI |  | SURP. | tmarquardt@leegov.com
|  |  | Mandated | [10 empty] | TOLLS
| TBD | Colonial Summerlin Flyover - Midpoint Bridge | Concurrency, LOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137000000 | 137000000 | CAPE/MP | TBD
SURP.
TOLLS
DEBT
1,4 | 200669 | Corkscrew Road | Reduce congestion/wait | 1825431 | 24525823 | 1000000 | 16068116 | 0 | 1400000 | 0 | 18468116 | 0 | 44819370 | IF25 | Dave Murphy
|  |  | time, Improved safety | DES | ROW/DES/MIT | ROW | CST/CEI |  | LS |  |  |  |  | Debt | dmurphy@leegov.com
GT
FDOT
CON
3 | 205067 | Estero Blvd. Improvements | Town request, congestion, | 48370003 | 31318170 | 0 | 0 | 0 | 0 | 0 | 0 |  | 79688173 | SANIBEL | Rob Phelan
|  |  | infrastructure conditions, | PRELIM/DES | DES/CST/CEI | [8 empty] | SURP. | rphelan@leegov.com
|  |  | Complete Streets | CST/CEI | [9 empty] | TOLLS
principals
|  |  | NM - Essential | [10 empty] | GT
4 | 200671 | Gateway at Griffin Roundabout | Improve safety without | 159603 | 390396 | 3220000 | 0 | 0 | 0 | 0 | 3220000 |  | 3769999 | GT | Dave Murphy
|  |  | adding delay | DES | DES/ROW | CST/CEI | [8 empty] | dmurphy@leegov.com
5 | 209246 | Gunnery Rd./8th St. Intersection Improvements | Intersection control |  | 1579817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1579817 | GT | Alex Slaibe
|  | Signalization and turn lane improvements | needed |  | DES/ROW | [8 empty] | FDOT | aslaibe@leegov.com
NM- Core Critical
5 | 205063 | Homestead 4L/Sunrise-Alabama | LOS, community interest | 13438332 | 9784294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23222626 | IF23/GT/ | Vince Miller, 533-8577
|  | 4L widening, south of Sunrise Blvd. to Alabama Rd., including on-road | Mandated | DES/ROW | DES/ROW/ | [8 empty] | GIF | vmiller@leegov.com
|  | bike lanes and sidewalks on both sides |  | CST, CEI | CST, CEI, LS
3 | 205083 | Hickory Bridge Replacements | Age | 0 | 0 | 0 | 6527180 | 0 | 0 | 0 | 6527180 | 58485805 | 65012985 | SANIBEL | Tom Marquardt
|  | Project combines New Pass, Little Carlos and Big Hickory bridge, including demolition and disposal of the olf bridges. | Condition of bridge (Bridge Health Index) |  |  |  | DES |  |  |  |  | CST/CEI |  | SURP. TOLLS | tmarquardt@leegov.com
5 | 200637 | Build two new signals on Lee Boulevard | Improve safety | 90967 | 609033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14859999 | IF22 | Mike Padgett
|  |  | Intersections meet signal | DES | DES, CST | [8 empty] | GT | mpadgett@leegov.com
|  | Lee Boulevard/Lee Street Traffic Signal | warrants and | [10 empty] | FDOT
|  | Lee Boulevard/Joan Avenue Traffic Signal | almost meet
crash warrants
4 | 205028 | Littleton Road | Congested | 1048073 | 13411926 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 14859999 | GT | Vince Miller
|  |  | Expected to worsen with | Study | DES/ROW | [6 empty] | LS |  | IF22 | vmiller@leegov.com
|  |  | Kismet/Littleton | [10 empty] | FDOT
2,4 | 240613 | Ortiz 4L/Colonial-MLK | Parallel reliever to I-75, | 822102 | 4022398 | 16519798 | 0 | 519000 | 0 | 0 | 17038798 | 0 | 21883298 | IF23 | Rob Phelan
|  |  | access to jail and EMS, | ROW/DES | DES/MIT | CST/CEI |  | LS | [5 empty] | GT | rphelan@leegov.com
LOS per Concurrenty Rpt,
|  |  | City tie-in of Hanson St.ext | [10 empty] | BP
4,5 | 204072 | Ortiz 4L/MLK-Luckett/Luckett-I75 | Parallel relief to I-75 | 9237336 | 554659 | 0 | 3714078 | 0 | 28474599 | 0 | 32188677 | 544000 | 42524672 | IF23 | Rob Phelan
|  |  | improve area circulation | DES/ROW | ROW |  | DES |  | CST/CEI |  |  | LS |  | GT | rphelan@leegov.com
|  |  | improve LOS | Project Mgmt
NM - Essential
ALL | 206759 | Signal System ATMS Upgrade | Maximizes efficient use | 5426932 | 1464400 | 750000 | 750000 | 750000 | 750000 | 750000 | 3750000 | 0 | 10641332 | GT | Mike Padgett
|  |  | of existing capacity | CST | CST | CST | CST | CST | CST | CST |  |  |  |  | mpadgett@leegov.com
|  |  | NM - Core Critical | Furniture & Equipment
2 | 204053 | Three Oaks Parkway Extension North | Extends major arterial, | 11370288 | 37998483 | 22776619 | 31720000 | 0 | 1050000 | 0 | 55546619 | 0 | 104915390 | IF23,24 | Vince Miller
|  |  | parallel reliever to I-75 | DES/ROW | DES/ROW | CST/CEI | CST/CEI |  | LS |  |  |  |  | GIF/GT | vmiller@leegov.com
|  |  | NM - Essential | Project Mgmt | CST/CEI
1,2,3 | 205818 | Toll Interoperability | Age of equipment, rapid | 502082 | 318086 | 150000 | 150000 | 150000 | 150000 | 150000 | 750000 | 0 | 1570168 | SURP. | Sue Drotleff
|  |  | technology changes | CST | CST | CST | CST | CST | CST | CST |  |  |  | TOLLS | sdrotleff@leegov.com
NM - Core Critical
1,2,3 | 200615 | Toll System Replacement | Age of equipment, rapid | 0 | 250000 | 0 | 13000000 | 0 |  | 0 | 13000000 | 0 | 13250000 | SURP. | Sue Drotleff
|  |  | technology changes |  | DES |  | CST | [6 empty] | TOLLS | sdrotleff@leegov.com
NM - Core Critical
| TBD | Veterans Parkway 6L Chiquita to Skyline Boulevard | LOS per Concurrency | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500000 | 8500000 | CAPE/MP | TBD
|  |  | Report | [10 empty] | SURP.
TOLLS
GT
MAJOR MAINTENANCE PROJECTS
CW | 404683 | Road Resurface/Rebuild Program | Pavement rating system, | 58486172 | 4537799 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 20000000 | 0 | 83023971 | GT | Dirk Danley
|  |  | complaints, asset prot. | CST | CST | CST | CST | CST | CST | CST |  |  |  |  | ddanley@leegov.com
5 | 406715 | Road Resurface/Rebuild Program - Lehigh Acres | Pavement rating system, | 17925369 | 6679949 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 25000000 | 0 | 49605318 | GIF | Dirk Danley
|  |  | complaints, asset prot. | CST | CST | CST | CST | CST | CST | CST |  |  |  |  | ddanley@leegov.com
| 403304 | Major Arterials Resurfacing | Paving rating system | 0 | 1150000 | 1150000 | 1150000 | 1150000 | 1150000 | 1150000 | 5750000 | 0 | 6900000 | GT | Dirk Danley
[6 empty] | CST | CST | CST | CST | CST |  |  |  |  | ddanley@leegov.com
CW | 405714 | Master Bridge Project | Bridge conditions, asset | 9840979 | 1652799 | 815000 | 825000 | 825000 | 825000 | 825000 | 4115000 | 0 | 15608778 | GT | Avelino Cancel
|  |  | protection | CST | CST | CST | CST | CST | CST | CST |  |  |  |  | acancel@leegov.com
Mandated
CW | 406024 | Roadway Beautification | Leescape Master Plan, | 4992430 | 186866 | 100000 | 100000 | 100000 | 100000 | 100000 | 500000 | 0 | 5679296 | GIF | Bob DeBrock
|  |  | RLAC priorities, com- | LS | LS | LS | LS | LS | LS | LS |  |  |  |  | bdebrock@leegov.com
munity interest
NM - Essential
CW | 406670 | Signal Upgrades/Equipment Replacement | Signal equipment con- | 2419929 | 644630 | 350000 | 350000 | 350000 | 350000 | 350000 | 1750000 | 0 | 4814559 | GT | Ryan Kirsch
|  |  | dition, safety | DES,CST | CST | CST | CST | CST | CST | CST |  |  |  |  | rkirsch@leegov.com
Mandated
CW | 406713 | Master Signal Project/Major Intersections | Intersection conditions/ | 13207653 | 2905989 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 7500000 | 0 | 23613642 | GT | Tom Marquardt
|  |  | needs | CST | CST | CST | CST | CST | CST | CST |  |  |  |  | tmarquardt@leegov.com
NM - Core Critical
CW | 406079 | ADA Plan Implementation | Federal Law, ADA plan | 1109288 | 640710 | 250000 | 250000 | 250000 | 250000 | 250000 | 1250000 | 0 | 2999998 | GT | Tom Marquardt
|  |  | County ADA Transition | DES,CST | CST | CST | CST | CST | CST | CST |  |  |  |  | tmarquardt@leegov.com
Plan
Mandated
CW | 406080 | Roadway Lighting Upgrade | Sustainability, operating | 1199979 | 1050021 | 450000 | 450000 | 450000 | 450000 | 450000 | 2250000 | 0 | 4500000 | GT | Ryan Kirsch
|  |  | cost reduction | CST | CST | CST | CST | CST | CST | CST |  |  |  |  | rkirsch@leegov.com
NM - Core Critical
CW | 406763 | Sign Replacement Program/Raised Pavement Markers | Sign conditions, safety, | 731192 | 170925 | 150000 | 150000 | 150000 | 150000 | 150000 | 750000 | 0 | 1652117 | GT | Dan Vasiloff
|  |  | liability | CST | CST | CST | CST | CST | CST | CST |  |  |  |  | dvasiloff@leegov.com
Mandated
CW | 408944 | Overhead Sign Structures Evaluation | Maintenance obligations, | 145974 | 634026 | 130000 | 130000 | 130000 | 130000 | 130000 | 650000 | 0 | 1430000 | GT | Ryan Kirsch
|  |  | liability, FDOT standards | Eval | CST | CST | CST | CST | CST | CST |  |  |  |  | rkirsch@leegov.com
Mandated
CW | 406714 | Signal Network | Need to keep the | 331879 | 206333 | 120000 | 120000 | 120000 | 120000 | 120000 | 600000 | 0 | 1138212 | GT | Rob Radford
|  |  | network secure | CST | CST | CST | CST | CST | CST | CST |  |  |  |  | rradford@leegov.com
NM - Essential
| 400950 | Traffic Signal Technology | Help drivers with real | 0 | 0 | 250000 | 250000 | 250000 | 250000 | 250000 | 1250000 | 0 | 1250000 | GT | Rob Price
|  |  | time warnings to | [11 empty] | rprice@leegov.com
pedestrians, bicycles and
drivers using Smart Car
connected vehicles
| TBD | Sidewalk Repair | Repair sidewalks | 0 | 0 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 5000000 | 0 | 5000000 | GT | Joey Wilson
|  |  | countywide |  |  | CST | CST | CST | CST | CST |  |  |  |  | jwilson@leegov.com
| 406713 | Colonial Safety Improvements US41/McGregor | Safety Improvements | 0 | 860000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 860000 | CAPE | Tom Marquardt
[5 empty] | CST | [8 empty] | MP | tmarquardt@leegov.com
SURP/
TOLLS
KEY (PHASES): |  | PRELIM = Preliminary Study; PD&E = Project Development & Environmental Study; DES = Design; ROW = Right-of-Way Acquisition; CST = Construction; CEI = Construction Engineering Inspection; PM = Project Management; LS = Landscaping;
MIT = Mitigation
KEY (FUNDS): |  | IF23 = Road Impact Fees from District 23; GT = Local Option Gas Taxes; FDOT = Florida Dept. of Transportation; GIF = Growth Increment Funding